## County Projects Stock Take
COUNTY GOVERNMENT OF KIAMBU
PROJECTS INVENTORY FROM FY 2013/2024 TO 2024/2025
S/No. | Project Name/Title | Sub-County | Ward | Project Start Date/expected start date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled)
EDUCATION, GENDER, CULTURE AND SOCIAL SERVICES
| FY 2014/15 |  | FY 2014/15
1 | Proposed ECD rehabilitation and refurbishment at Thogoto Nursery school | Kikuyu | Kikuyu Township | 2014-01-01 | 2014-05-01 |  | 1778100 | Completed
2 | Proposed classrooms (ECD) rehabilitation and refurbishment at Uthiru Nursery school, Kiambu | Kabete | Uthiru | 2014-01-01 | 2014-04-01 |  | 2015070 | Completed
3 | Proposed classroom rehabilitation and refurbishment of Kinoo Youth polytechnic, Kiambu | Kikuyu | Kinoo | 2014-02-01 | 2014-04-01 |  | 3945600 | Completed
4 | Proposed classroom rehabilitation and refurbishment of Thogoto Youth polytechnic, Kiambu | Kikuyu | Kikuyu Township | 2014-01-01 | 2014-04-01 |  | 3366251 | Completed
5 | Proposed classroom rehabilitation and refurbishment of Uthiru Youth polytechnic, Kiambu | Kabete | Uthiru | 2014-01-01 | 2014-04-01 |  | 3558326 | Completed
6 | Proposed classrooms (ECD) rehabilitation and refurbishment at Shauri Yako Nursery school, Kiambu | Kikuyu | Kikuyu Township | 2014-01-01 | 2014-05-01 |  | 1564839 | Completed
7 | Proposed classrooms (ECD) rehabilitation and refurbishment at PCEA Thamanda Nursery school, Kiambu | Kikuyu | Sigona | 2014-01-01 | 2014-04-01 |  | 1884410 | Completed
8 | Proposed Ablution block at Garrisa road ECDE centre | Thika | Thika Township | 2014-2015 | 2016 |  | 1444254 | Completed
9 | Proposed Construction of a model twin ECDE centre at Gitamaiyu primary ECDE with office and a toilet | Kiambu | Riabai | 2014 | 2026-11-14 |  | 3694360 | Completed
FY 2015/16
10 | Proposed classroom rehabilitation and refurbishment of Ting’ang’a Youth polytechnic, Kiambu | Kiambu | Ting’ang’a | 2015-06-01 | 2016 |  | 2946698 | Completed
11 | Proposed construction of classroom / workshop block at Kirangari Polytechnic | Kabete | Nyathuna | 2015 | 2016-05-01 |  | 2785438 | Completed
12 | Proposed ablution block at Limuru model ECD centre | Limuru | Limuru Central | 2015 | 2016 |  | 1496870 | Completed
13 | Proposed construction of classroom / workshop block at Nyanduma Polytechnic kiambu | Lari | Nyanduma | 2015 | 2016 |  | 2928580 | Completed
14 | Proposed construction of two number classrooms and fencing at Kabunge ECDE | Lari | Lari Kirenga | 2026-05-15 | 2016 |  | 3399570 | Completed
15 | Proposed construction of one number classroom at Kirenga Polytechnic | Lari | Lari Kirenga | 2015 | 2016 |  | 2903850 | Completed
16 | Proposed two number classrooms and pit latrine at Kwangethe ECDE centre, Kiu Ward | Ruiru | Kiuu | 2015 | 2016 |  | 3552890 | Completed
17 | Proposed construction of two number storeyed classrooms at Kanyariri Polytechnic | Kabete | Gitaru | 2015 | 2016 |  | 4890630 | Completed
18 | Proposed construction of St. John Bosco ECDE two number classrooms and ablution block | Limuru | Bibirioni | 2015 | 2017-01-01 |  | 3569910 | Completed
19 | Proposed rehabilitation of building and construction of one number classroom at Kairi polytechnic | Gatundu North | Chania | 2026-01-15 | 2016-01-01 |  | 2421165 | Completed
20 | Proposed ablution block at Garisa road ECDE centre | Thika | Thika Township | 2026-01-15 | 2026-06-16 |  | 1444254 | Completed
21 | Proposed rehabilitation of classrooms and construction of a toilet block at Githunguri ECDE centre | Ruiru | Biashara | 2026-01-15 | 2016-06-01 |  | 1987202 | Completed
22 | Rehabilitation of classrooms and construction of a toilet block at Ngoliba ECDE centre | Thika | Ngoliba | 2026-01-15 | 2016-06-01 |  | 1633528 | Completed
23 | Proposed rehabilitation of classrooms and construction of a toilet block at Githunguchu ECDE centre | Limuru | Ndeiya | 2026-01-15 | 2016-06-01 |  | 1956491.2 | Completed
24 | Proposed construction of ablution block at Mwihoko ECDE centre | Ruiru | Mwihoko | 2026-01-15 | 2016-04-01 |  | 1474785 | Completed
25 | Proposed construction of Wabeni youth polytechnic workshop and office | Thika | Thika Township | 2026-01-15 | 2016 |  | 2394490 | Completed
26 | Proposed construction of one number classroom and toilet block at Juja ECDE centre | Juja | Juja | 2015 | 2016 |  | 1956866 | Completed
27 | Proposed rehabilitation of classrooms and construction of toilet block at Ngoliba ECDE center | Thika | Ngoliba | 2015-2016 | 2016 |  | 1633528 | Completed
28 | Proposed rehabilitation of classrooms and construction of a toilet block at Mukurwe ECDE centre | Gatundu North | Mang’u | 2026-01-15 | 2016 |  | 1955200 | Completed
| FY 2016/17 |  |  | FY 2016/17
29 | Proposed construction of two number ECDE classrooms and ablution block at Gichana primary school | Limuru | Ngecha Tigoni | 2026-06-16 | 2017 |  | 3580280 | Completed
30 | Proposed construction of two number ECDE classrooms and an ablution block at Utugi ECDE centre | Lari | Kinale | 2026-06-16 | 2017 |  | 3670845 | Completed
31 | Proposed one number ECDE classroom at Tinganga model primary school | Kiambu | Ting’ang’a | 2026-06-16 | 2017 |  | 2699220 | Completed
32 | Proposed refurbishment to Muguga Polytechnic, Kiambu | Kabete | Muguga | 2026-07-16 | 2017-03-01 |  | 2773170 | Completed
33 | Proposed construction of two number classrooms and ablution block at Kago ECDE centre | Lari | Kijabe | 2026-07-16 | 2017-02-01 |  | 3503475 | Completed
34 | Proposed two number ECDE classrooms and ablution block Muthandi ECDE centre, Kiambu | Githunguri | Ikinu | 2016 | 2017 |  | 3597730 | Completed
35 | Proposed construction of two number classrooms and ablution block at Kawaida ECDE | Kiambaa | Kihara | 2026-07-16 | 2017-01-01 |  | 3495730 | Completed
36 | Proposed one number ECDE classroom and ablution block at Njunu ECDE centre | Githunguri | Githiga | 2026-07-16 | 2017-02-01 |  | 2699405 | Completed
37 | Proposed facility rehabilitation and refurbishment at Mangu Youth Polytechnic | Thika | Gatuanyaga | 2026-07-16 | 2017-05-01 |  | 2750000 | Completed
38 | Proposed construction of two number classrooms and a toilet block at Kahembeta ECDE centre, Gituamba Ward | Gatundu North | Gituamba | 2026-07-16 | 2016-12-01 |  | 4320432 | Completed
39 | Proposed rehabilitation and refurbishment of workshop at Kagumo-ini Polytechnic | Gatundu South | Chania | 2026-07-16 | 2017-05-01 |  | 2783720 | Completed
40 | Proposed construction of two number twin workshops, principal’s office plus secretary at Kwihota youth polytechnic | Ruiru | Kahawa Wendani | 2026-07-16 | 2017 |  | 4996215 | Completed
| FY 2017/18 |  | FY 2017/18
41 | Proposed construction of two number classrooms with offices, toilet block and fencing at Nachu ECDE | Kikuyu | Nachu | 2026-07-17 | 2018-02-01 |  | 5731390 | Completed
| FY 2018/19 |  | FY 2018/19
42 | Renovation works at Biafra ECDE and Construction of perimeter fence | Thika | Hospital | 2018-02-01 | 2018-07-01 |  | 3992300 | Completed
43 | Construction of perimeter fence at Bahati ECDE (phase 2) | Thika | Gatuanyaga | 2018-03-01 | 2018-05-01 |  | 3840240 | Completed
44 | Proposed Construction of a pit latrine at Kiawaroga ECDE Centre | Limuru | Ndeiya | 2018-03-01 | 2018-08-01 |  | 1537271 | Completed
| FY 2019/20 |  | FY 2019/20
45 | Proposed Construction Of A Classroom Block And A Toilet Block At Jacob Wells ECDE Centre | Juja | Murera | 2019-08-01 | 2022-01-01 |  | 4994530 | Completed
46 | Proposed Construction of Motor Vehicle Garage at Wabeni Vocational Training Centre | Thika | Thika Township | 2020 | 2021 |  | 1025180 | Completed
| FY 2021/22 |  | FY 2021/22
47 | Proposed Construction Of Twin Classrooms At Igamba Primary | Gatundu North | Githobokoni | 2021-03-01 | 2021-05-01 |  | 3226930 | Completed
48 | Proposed Construction Of Toilet Block At Gataka ECDE Centre | Githunguri | Githiga | April | 2021-06-01 |  | 1094584 | Completed
49 | Proposed Construction Of Toilet Block At Mbauni ECDE Centre | Lari | Kijabe | April | 2021-06-01 |  | 1187768.11 | Completed
50 | Proposed Construction Of Toilet Block At Magina ECDE Centre | Lari | Kijabe | April | 2021-06-01 |  | 1187852.31 | Completed
51 | Proposed Construction Of Twin Classrooms At Igamba Primary | Gatundu North | Githobokoni | 2021-03-01 | 2021-05-01 |  | 3226930 | Completed
52 | Proposed Construction Of Toilet Block At Gataka ECDE Centre | Githunguri | Githiga | April | 2021-06-01 |  | 1094584 | Completed
53 | Proposed Construction Of Twin Classrooms At KahawaWendaniPrimary | Ruiru | Kahawa Wendani | 2026-04-22 | 2022-09-01 |  | 3674750 | Completed
| FY 2023/24 |  | FY 2023/24
54 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Barracks | Thika | Kamenu | 2023-12-01 | 2024-02-01 |  | 3591900 | Completed
55 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Umoja Primary | Thika | Hospital | 2023-12-01 | 2024-02-01 |  | 3684201 | Completed
56 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Power-line Primary | Thika | Ngoliba | 2023-12-01 | 2024-02-01 |  | 3693790 | Completed
57 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at KiganjoEcd | Thika | Kamenu | 2023-12-01 | 2024-02-01 |  | 3697200 | Completed
58 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at KamenuEcd | Thika | Kamenu | 2023-12-01 | 2024-02-01 |  | 3665600 | Completed
60 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Umoja Primary | Thika | Hospital | 2023-12-01 | 2024-02-01 |  | 3684201 | Completed
61 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at G.S.U Primary | Juja | Murera | 2023-05-01 | 2024-02-01 |  | 2940000 | Completed
62 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Muthara Primary | Juja | Witeithie | 2023-09-23 | 2024-02-01 |  | 3618780 | Completed
63 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Ndururumo Ecde | Juja | Theta | 2023-12-01 | 2024-02-01 |  | 3699190 | Completed
64 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at KaramaniEcd | Juja | Murera | 2023-12-01 | 2024-02-01 |  | 3698180 | Completed
65 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Kairi ka Mariguini | Gatundu North | Chania | 2023-12-01 | 2024-02-01 |  | 3575150 | Completed
66 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Gakunju Primary | Gatundu South | Kiamwangi | 2023-12-01 | 2024-02-01 |  | 3681060 | Completed
67 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Kiangunu Primary | Gatundu North | Gituamba | 2023-12-01 | 2024-02-01 |  | 3699820 | Completed
68 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Munyaka Primary | Gatundu North | Githobokoni | 2023-12-01 | 2024-02-01 |  | 3698260 | Completed
69 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Mutuma Primary | Gatundu North | Mang’u | 2023-12-01 | 2024-02-01 |  | 3705980 | Completed
70 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Makwa | Gatundu North | Chania | 2023-12-01 | 2024-02-01 |  | 3698621 | Completed
71 | Proposed Completion of Workshop and Offices at Wabeni Vocational Training Center | Thika | Thika Township | 2023 | 2024-06-01 |  | 2413360 | Completed
72 | Proposed Construction of Administration Block at Makongeni VTC | Thika | Kamenu | 2023 | 2024-06-01 |  | 4999330 | Completed
73 | Twin Workshop At Sigona Vtc | Kikuyu | Sigona | 2023-09-01 | 2024-10-01 |  | 4951160 | Completed
74 | Twin Workshop AtRuiru Township Vtc | Ruiru | Biashara | 2026-05-23 | 2024-06-01 |  | 3996937 | Completed
75 | Twin Workshop Completion AtRiabaiVtc | Kiambu | Riabai | 2026-09-23 | 2023-12-01 |  | 2494415 | Completed
76 | Renovation At KirangariVtc | Kabete | Nyathuna | 2026-12-23 | 2024-06-01 |  | 4787200 | Completed
77 | Boundary Wall At Kirangari Vtc | Kabete | Nyathuna | 2026-12-23 | 2026-12-24 |  | 7973100 | Completed
78 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Kiu River ECDE | Kiambu | Ting’ang’a | Nov 2023 | 2024-04-01 |  | 3655550 | Completed
79 | Renovation Works Of A 2no. ECDE Classroom Block At Ngegu Primary School | Kiambu | Kiambu Township | 2023-11-01 | 2024-02-01 |  | 2490785 | Completed
80 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Wamita | Gatundu South | Gituamba | 2023-08-01 | 2023-12-01 |  | 3616000 | Completed
81 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Kagema Primary | Githunguri | Githiga | 2023-08-01 | 2023-12-01 |  | 3633610 | Completed
82 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Tharauni Primary | Limuru | Limuru Central | 2023-08-01 | 2024-01-01 |  | 3653920 | Completed
83 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Bariki Community | Lari | Nyanduma | 2023-08-01 | 2023-12-01 |  | 3655470 | Completed
84 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Kibichiku primary ECDE | Kabete | Kabete | 2026-11-23 | 2024-05-01 |  | 3636135 | Completed
85 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Thika Primary | Thika | Hospital | 2024-02-01 | 2024-04-01 |  | 3699980 | Completed
86 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Gatuanyaga | Thika | Gatuanyaga | 2024-02-01 | 2024-04-01 |  | 3693790 | Completed
87 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Matathia | Thika | Ngoliba | 2024-02-01 | 2024-04-01 |  | 3693790 | Completed
88 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Kisiwa Primary | Thika | Thika Township | 2024-02-01 | 2024-04-01 |  | 3697730 | Completed
89 | Proposed Completion of model twin E.C.D.E classroom with Offices and Toilet block at G.S.U Primary | Juja | Murera | 2026-04-24 | 2024-06-01 |  | 2876160 | Completed
90 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Mwea | GatunduNorth | Chania | 2024-02-01 | 2024-04-01 |  | 3699970 | ongoing
91 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at Miiri | GatunduNorth | Githobokoni | 2024-02-01 | 2024-04-01 |  | 3699910 | Completed
92 | Proposed Construction of model twin E.C.D.E classroom with Offices and Toilet block at ST. Ann Maria-ini | GatunduNorth | Gituamba | 2024-02-01 | 2024-04-01 |  | 3698955 | Completed
93 | Proposed Construction of model E.C.D.E at Mukuyu-ini | Juja | Kalimoni | 2024-02-01 | 2024-04-01 |  | 3660320 | Completed
94 | Proposed Completion of model E.C.D.E at Munyu ECDE | Thika | Gatuanyaga | 2024-02-01 | 2024-04-01 |  | 2198550 | Completed
95 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Mutonya Community Centre ECDE | Ruiru | Gatong’ora | 2024-02-01 | 2024-05-01 |  | 3696070 | Completed
96 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Gitothua Primary | Ruiru | Gitothua | 2024-02-01 | 2024-05-01 |  | 3662960 | Completed
97 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Ndumberi Primary | Kiambu | Ndumberi | 2024-02-01 | 2024-06-01 |  | 3687900 | Completed
98 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At St Ann Kihingo | Kiambu | Riabai | 2024-02-01 | 2024-06-01 |  | 3687900 | Completed
99 | Construction Of Model Twin E.C.D.E Classroom With Offices And Toilet Block At Mahinga Primary | Limuru | Ndeiya | 2024-02-01 | 2024-05-01 |  | 3680750 | Completed
100 | Proposed Construction of model ECDE classroom with offices and a toilet block at Gatune Primary | Kikuyu | Karai | 2026-01-24 | 2024-06-01 |  | 3698153 | Completed
101 | Proposed Construction of model ECDE classroom with offices and a toilet block at Gathiru Primary | Lari | Kijabe | 2026-01-24 | 2024-07-01 |  | 3661835 | Completed
102 | Proposed construction of a model ECDE centre at Matathia ECDE centre in Kijabe ward | Lari | Kijabe | 2026-02-24 | 2024-08-01 |  | 3352930 | Completed
103 | Proposed construction of a model ECDE centre at Crossroads ECDE centre in Kinale ward | Lari | Kinale | 2026-02-24 | 2024-08-01 |  | 3546180 | Completed
104 | Proposed construction of a model twin ECDE classroom with offices and toilet Block at Kambaaprimary model ECDE | Lari | Kijabe | 2026-02-24 | 2024-08-01 |  | 3629664 | Completed
105 | Proposed construction of a model twin ECDE classroom with offices and toilet Block at Githirioni primary model ECDE | Lari | Kinale | 2026-02-24 | 2024-08-01 |  | 3696552 | Completed
106 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Kibiku Primary | Kabete | Nyathuna | 2026-01-24 | 2024-09-01 |  | 3659915 | Completed
107 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Muguga Primary | Kabete | Muguga | 2026-01-24 | 2024-09-01 |  | 3630875 | Completed
108 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Kamuguga Primary | Kabete | Muguga | 2026-01-24 | 2024-09-01 |  | 3661835 | Completed
109 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Nguriunditu Primary | Kikuyu | Karai | 2026-03-24 | 2024-09-01 |  | 3673665 | Completed
110 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Mahiaini Primary | Kabete | Nyathuna | 2026-03-24 | 2024-09-01 |  | 3659915 | Completed
111 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at St.Marys Kaimba Primary | Kabete | Nyathuna | 2026-03-24 | 2024-09-01 |  | 3680500 | Completed
112 | Proposed construction of model Twin ECDE classroom with offices and an ablution block at Ngure Primary | Kabete | Gitaru | 2026-01-24 | 2026-01-25 |  | 3698835 | Completed
113 | Proposed construction of model ECDE classroom with offices and toilet block at Kinyogori Primary School ECDE | Limuru | Bibirioni | 2026-01-24 | 2026-06-24 |  | 3690450 | Completed
114 | Proposed construction of model ECDE classroom with offices and toilet block at Bosco Primary School ECDE | Limuru | Limuru Central | 2026-01-24 | 2026-06-24 |  | 3686300 | Completed
115 | Proposed construction of model ECDE classroom with offices and toilet block at Nyataragi Primary School ECDE | Limuru | Limuru Central | 2026-05-24 | 2026-01-25 |  | 3665600 | Completed
116 | Proposed construction of model ECDE classroom with offices and toilet block at Gacii ECDE | Kiambaa | Kihara | 2026-02-24 | 2026-06-24 |  | 3665600 | Completed
117 | Proposed construction of model ECDE classroom with offices and toilet block at Waguthu ECDE | Kiambaa | Cianda | 2026-02-24 | 2026-06-24 |  | 3688570 | Completed
118 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Ndongoro primary ECDE | Kabete | Kabete | 2026-02-24 | 2026-08-24 |  | 3687740 | Completed
119 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Thigio community ECDE | Limuru | Ndeiya | 2026-02-24 | 2026-05-24 |  | 3673950 | Completed
120 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Kirenga primary ECDE | Lari | Lari Kirenga | 2026-01-24 | 2026-06-24 |  | 3670360 | Completed
121 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Kamburu primary ECDE | Lari | Kamburu | 2026-01-24 | 2026-06-24 |  | 3696552 | Completed
122 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Githirioni pry ECDE | Lari | Kinale | 2026-01-24 | 2026-05-24 |  | 3696552 | Completed
123 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Limuru Mission Primary | Limuru | Limuru East | 2026-01-24 | 2026-06-24 |  | 3670360 | Completed
124 | Proposed Construction of a model twin ECDE classrooms with offices and a toilet block at Wambaa Primary | Kikuyu | Karai | 2026-01-24 | 2026-06-24 |  | 3670360 | Completed
125 | Proposed Construction of a model twin ECDE centre at Githunguchu primary ECDE with office and a toilet | Limuru | Ndeiya | 2026-01-24 | 2026-11-24 |  | 3685800 | Completed
126 | Proposed Construction of a model twin ECDE centre at Kirasha primary ECDE with office and a toilet | Lari | Kinale | 2026-01-24 | 2026-11-24 |  | 3696460 | Completed
127 | Proposed Construction of a model twin ECDE centre at Kabukuprimary ECDE with office and a toilet | Limuru | Ngecha Tigoni | 2026-01-24 | 2026-11-24 |  | 3678510 | Completed
| FY 2024/25 |  | FY 2024/25
128 | Proposed Construction of Model ECDE Centre With Offices And Toilet Block At Gachororo Community | Juja | Juja | 2024-11-01 | 2025-03-01 |  | 4199100 | Completed
129 | Proposed Construction of Model ECDE Centre With Offices And Toilet Block At Ngethu ECDE Centre | Gatundu North | Gituamba | 2024-11-01 | 2025-03-01 |  | 4180464 | On-going
130 | Proposed Construction of Model ECDE Centre With Offices And Toilet Block At Thuraku ECDE Centre | Gatundu North | Githobokoni | 2024-11-01 | 2025-03-01 |  | 4178674 | Completed
131 | Proposed Construction of Model ECDE Centre With Offices And Toilet Block At Karure ECDE Centre | Gatundu North | Mang’u | 2024-11-01 | 2025-03-01 |  | 4179616 | Completed
132 | Proposed Construction of Model ECDE Centre With Offices And Toilet Block At Kamwangi ECDE Centre | Gatundu North | Chania | 2024-11-01 | 2025-03-01 |  | 4182334 | Completed
133 | Proposed Construction of Model Twin ECDE Classroom With Offices and a Toilet at Ndula Community Centre | Thika | Gatuanyaga | 2024-11-01 | 2025-03-01 |  | 4199280 | Completed
134 | Proposed Construction of Model Twin ECDE Classroom With Offices and a Toilet at Maguguni ECDE Centre | Thika | Ngoliba | 2024-11-01 | 2025-03-01 |  | 4199450 | Completed
135 | Proposed Construction of Model ECDE Centre With Offices and Toilet Block at Kimuchu | Thika | Kamenu | 2024-11-01 | 2025-03-01 |  | 4190830 | Completed
136 | Proposed Construction of Model ECDE Centre With Offices and Toilet Block at Ndekoma | Juja | Murera | 2024-11-01 | 2025-03-01 |  | 2944040 | Completed
137 | Proposed Construction of Model ECDE Centre With Offices and Toilet Block at Magomano | Juja | Theta | 2024-11-01 | 2025-03-01 |  | 4199894 | Completed
138 | Proposed completion of a model ECDE centre at Thirime | Kikuyu | Kikuyu Township | 2024-08-01 | 2024-12-01 |  | 2010795 | Completed
139 | Proposed construction of a model ECDE classrooms with offices and a toilet block at Manguo Pry School | Limuru | Limuru Central | 2024-08-01 | 2024-12-01 |  | 4196575 | Completed
140 | Proposed construction of a model ECDE classrooms with offices and a toilet block at Rongai Pry School | Limuru | Bibirioni | 2024-08-01 | 2024-12-01 |  | 4152340 | Completed
141 | Proposed completion of a model ECDE centre at Baraniki in Kikuyu Ward | Kikuyu | Kikuyu Township | 2024-08-01 | 2024-12-01 |  | 2580640 | Completed
142 | Proposed construction of a model twin ECDE classrooms with offices and a toilet block at Tigoni model ECDE centre | Limuru | Ngecha Tigoni | 2024-08-01 | 2024-12-01 |  | 4190085 | Completed
143 | Twin Workshop With Administration Offices Completion KwihotaVtc | Ruiru | Kahawa Wendani | May 2024 | Dec 2024 |  | 4199220 | Ongoing
144 | Proposed completion of a model ECDE centre at Thirime | Kikuyu | Kikuyu Township | 2026-08-24 | 2026-12-24 |  | 2010795 | Completed
145 | Proposed construction of a model ECDE classrooms with offices and a toilet block at Manguo Pry School | Limuru | Limuru Central | 2026-08-24 | 2026-12-24 |  | 4196575 | Completed
146 | Proposed construction of a model ECDE classrooms with offices and a toilet block at Rongai Pry School | Limuru | Bibirioni | 2026-08-24 | 2026-12-24 |  | 4152340 | Completed
147 | Proposed completion of a model ECDE centre at Baraniki in Kikuyu Ward | Kikuyu | Kikuyu Township | 2026-08-24 | 2026-12-24 |  | 2580640 | Completed
148 | Proposed construction of a model twin ECDE classrooms with offices and a toilet block at Tigoni model ECDE centre | Limuru | Ngecha Tigoni | 2026-08-24 | 2026-12-24 |  | 4190085 | Completed
149 | Proposed construction of a model twin ECDE classrooms with offices and a toilet block at St. Paul model ECDE centre | Limuru | Ngecha Tigoni | 2026-08-24 | 2026-12-24 |  | 4190085 | Completed
150 | Proposed construction of a model ECDE centre at Nduma primary | Kikuyu | Sigona | 2026-08-24 | 2026-12-24 |  | 4244990 | Completed
151 | Proposed construction of model ECDE centre with offices and a toilet block at Rironi model ECDE | Limuru | Limuru Central | 2026-08-24 | 2026-12-24 |  | 4193142 | Completed
152 | Proposed construction of model ECDE centre with offices and toilet block at Mai-a-ihii in Karai Ward | Kikuyu | Karai | 2026-08-24 | 2026-12-24 |  | 4199850 | Completed
153 | Proposed construction of a model twin ECDE classrooms with offices and a toilet block at Gicharani ECDE Primary | Kikuyu | Karai | 2024-07-01 | 2025-02-01 |  | 4053660.6 | Completed
154 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gachoire | Lari | Nyanduma | 2026-09-24 | 2026-12-24 |  | 4199885 | Completed
155 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gitithia | Lari | Lari Kirenga | 2026-09-24 | 2026-12-24 |  | 4199890 | Completed
156 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ikinu | Githunguri | Ikinu | 2026-09-24 | 2026-12-24 |  | 4199790 | Ongoing
157 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Karia | Githunguri | Ikinu | 2026-09-24 | 2026-12-24 |  | 4199890 | Ongoing
158 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kibagare | Lari | Lari Kirenga | 2026-09-24 | 2026-12-24 |  | 4133650 | Completed
159 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Komothai | Githunguri | Komothai | 2026-09-24 | 2026-12-24 |  | 4199680 | Ongoing
160 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Matuguta | Githunguri | Githiga | 2026-09-24 | 2026-12-24 |  | 4199790 | Completed
161 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Miugu | Gatundu North | Gituamba | 2026-09-24 | 2026-12-24 |  | 4201564 | Completed
162 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kimiritia | Gatundu South | Kiganjo | 2026-09-24 | 2026-12-24 |  | 4197760 | Completed
163 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ack Kamiti Anmer | Kiambu | Ting'ang'a | 2026-09-24 | 2026-12-24 |  | 4171380 | Completed
164 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ack Karura | Kiambaa | Ndenderu | 2026-09-24 | 2026-12-24 |  | 4115430 | Completed
165 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Athi | Juja | Kalimoni | 2026-09-24 | 2026-12-24 |  | 4197495 | Completed
166 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Chief Wandie | Kiambu | Riabai | 2026-09-24 | 2026-12-24 |  | 4197495 | Completed
167 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gachororo | Juja | Juja | 2026-09-24 | 2026-12-24 |  | 4174830 | Completed
168 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gataara | Kabete | Gitaru | 2026-09-24 | 2026-12-24 |  | 4050630 | Completed
169 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gatei | Gatundu North | Githobokoni | 2026-09-24 | 2026-12-24 |  | 4074750 | Completed
170 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gathiga | Kabete | Nyathuna | 2026-09-24 | 2026-12-24 |  | 4194893 | Completed
171 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gatitu | Githunguri | Githiga | 2026-09-24 | 2026-12-24 |  | 4196571 | Completed
172 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gatitu ECDE | Gatundu South | Kiamwangi | 2026-09-24 | 2026-12-24 |  | 4180714 | Completed
173 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gikobu ECDE | Gatundu North | Ndarugu | 2026-09-24 | 2026-12-24 |  | 4183478 | Completed
174 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Gikumari | Ruiru | Gatong’ora | 2026-09-24 | 2026-12-24 |  | 4298460 | Completed
175 | Proposed Construction of Model ECDE Centre With Offices and Toilet Block At Githunguri Ranching | Ruiru | Biashara | 2026-09-24 | 2026-12-24 |  | 4198194 | Completed
176 | Proposed Construction of Model ECDE Centre With Offices and Toilet block at Ihiga | Githunguri | Githiga | 2026-09-24 | 2026-12-24 |  | 4199990 | Completed
177 | Proposed Construction Of Model ECDE Centre With Offices and Toilet block at Ituru | Gatundu South | Ng’enda | 2026-09-24 | 2026-12-24 |  | 4191895 | Completed
178 | Proposed Construction Of Model ECDE Centre With Offices and Toilet block at Kagumoini primary | Gatundu South | Ng’enda | 2026-09-24 | 2026-12-24 |  | 4198800 | Completed
179 | Proposed Construction of Twin classroom with Offices and ablution block at King'eero ECDE Centre | Kabete | Kabete | 2026-09-24 | 2026-12-24 |  | 4072000 | Completed
180 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block at Thindigua ECDE centre | Kiambu | Kiambu Township | 2026-09-24 | 2026-12-24 |  | 4192310 | Ongoing
181 | Proposed Construction Of Model ECDE Centre With Offices and Toilet block at Kanyiha | Kikuyu | Nachu | 2026-09-24 | 2026-12-24 |  | 4244980 | Completed
182 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Karenge | Lari | Nyanduma | 2026-09-24 | 2026-12-24 |  | 4199885 | Completed
183 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Karunga | Kiambu | Ndumberi | 2026-09-24 | 2026-12-24 |  | 4160820 | Completed
184 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Karura Ka Nyungu ECDE | Kabete | Nyathuna | 2026-09-24 | 2026-12-24 |  | 4198128 | Completed
185 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kawaida Community | Kiambaa | Cianda | 2026-09-24 | 2026-12-24 |  | 4168380 | Completed
186 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiambu Township | Kiambu | Kiambu Township | 2026-09-24 | 2026-12-24 |  | 4148090 | Completed
187 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiambururu | Githunguri | Ngewa | 2026-09-24 | 2026-12-24 |  | 4197401 | Completed
188 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiamugo | Gatundu South | Kiganjo | 2026-09-24 | 2026-12-24 |  | 4192839 | Completed
189 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiamworia ECDE | Gatundu South | Kiganjo | 2026-09-24 | 2026-12-24 |  | 4192215 | Completed
190 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kianjau | Thika | Thika Township | 2026-09-24 | 2026-12-24 |  | 4148600 | Completed
191 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiawanda ECDE | Kikuyu | Ndeiya | 2026-09-24 | 2026-12-24 |  | 4199123 | Completed
192 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kibii | Juja | Juja | 2026-09-24 | 2026-12-24 |  | 4695110 | Completed
193 | Proposed Construction Of Model ECDE Centre With Office And Toilet Block At Kihuririo ECDE | Githunguri | Komothai | 2026-09-24 | 2026-12-24 |  | 4155145 | Completed
194 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kimiritia In Kiganjo Ward. | Gatundu South | Kiganjo | 2026-09-24 | 2026-12-24 |  | 4197760 | Completed
195 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kirangari ECDE | Kabete | Nyathuna | 2026-09-24 | 2026-12-24 |  | 4192053 | Completed
196 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kiratina | Ruiru | Gatong’ora | 2026-09-24 | 2026-12-24 |  | 4297860 | Completed
197 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kitamaiyu | Githunguri | Komothai | 2026-09-24 | 2026-12-24 |  | 4199970 | Completed
198 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Kumura | Juja | Theta | 2026-09-24 | 2026-12-24 |  | 4149630 | Completed
199 | Proposed Completion Of Model ECDE Centre With Offices And Toilet Block At Miiri | Githunguri | Githunguri | 2026-09-24 | 2026-12-24 |  | 4201564 | Completed
200 | Proposed Completion Of ECDE Centre At Muchatha Primary In Muchatha Ward | Kiambaa | Muchatha | 2026-09-24 | 2026-12-24 |  | 2624371 | Completed
201 | Proposed Construction Of Model ECDE Centre With OfficesAnd Toilet Block At Mugutha | Juja | Murera | 2026-09-24 | 2026-12-24 |  | 4193285 | Completed
202 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Muhoho | Gatundu South | Kiganjo | 2026-09-24 | 2026-12-24 |  | 4186734 | Completed
203 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Muirungi | Lari | Kamburu | 2026-09-24 | 2026-12-24 |  | 4199890 | Completed
204 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Muti Mumu | Gatundu South | Kiamwangi | 2026-09-24 | 2026-12-24 |  | 4215040 | Completed
205 | Proposed Construction Of A Perimeter Wall At Mutonya | Ruiru | Gatong’ora | 2026-09-24 | 2026-12-24 |  | 4395767 | Completed
206 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Mwalimu Farm | Ruiru | Gatong’ora | 2026-09-24 | 2026-12-24 |  | 4198863 | Completed
207 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ndararua | Kabete | Gitaru | 2026-09-24 | 2026-12-24 |  | 4190183 | Completed
208 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Nderi | Kikuyu | Sigona | 2026-09-24 | 2026-12-24 |  | 4216980 | Completed
209 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ndiguini | Kikuyu | Nachu | 2026-09-24 | 2026-12-24 |  | 4118830 | Completed
210 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ndiini | Ruiru | Kahawa Sukari | 2026-09-24 | 2026-12-24 |  | 4395767 | Completed
211 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Nembu | Gatundu South | Kiamwangi | 2026-09-24 | 2026-12-24 |  | 4100115 | Completed
213 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At New Toll | Juja | Murera | 2026-09-24 | 2026-12-24 |  | 4084209 | Completed
214 | Proposed Construction Of Model ECDE Centre With Offices at Kiairia ECDE centre | Githunguri | Githunguri | 2026-09-24 | 2026-12-24 |  | 4278500 | Ongoing
215 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Nyamuthanga | Lari | Kamburu | 2026-09-24 | 2026-12-24 |  | 4191895 | Completed
216 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Qrs In Hospital Ward | Thika | Hospital | 2026-09-24 | 2026-12-24 |  | 4186360 | Completed
217 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Ruera | Juja | Murera | 2026-09-24 | 2026-12-24 |  | 4052070 | Completed
218 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Rungiri | Kabete | Gitaru | 2026-09-24 | 2026-12-24 |  | 4163313 | Completed
219 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Thika Muslim | Thika | Hospital | 2026-09-24 | 2026-12-24 |  | 4196805 | Completed
220 | Proposed Construction Of Model ECDE Centre With Offices And Toilet Block At Wangige | Kabete | Muguga | 2026-09-24 | 2026-12-24 |  | 4197050 | Completed
FINANCE, ICT AND ECONOMIC PLANNING
FY 2020/2021
1 | Red Nova Networking & ICT Installation | Kiambu | Kiambu township | 2021-01-01 | 2022-06-01 | 2022-06-01 | 15593717 | Complete
FY 2022/2023
2 | Mwiki ICT hub -Supply delivery of furniture and networking | Ruiru | Mwiki | 2022-07-01 | 2023-06-01 | 2024-06-01 | 4668240 | Complete
FY 2023/2024
3 | Githurai ICT hub -Supply delivery of furniture and networking | Ruiru | Githurai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3975442 | Complete
4 | Thika Data center UPS | Thika | Thika | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1500000 | Complete
5 | Networking of Juja sub county offices | Juja | Juja | 2023-11-01 | 2023-12-01 | 2023-12-01 | 2976527 | Complete
FY 2024/2025
6 | Local Area Network – Lari Sub county Office | Lari | Lari | 2025-04-01 | 2025-06-01 | 2025-06-01 | 2984732.5 | Complete
TRADE, INDUSTRIALIZATION, TOURISM AND INVESTMENT
FY 2015/2016
1 | Proposed construction of a market at Karuri | Kiambaa | Karuri | 2015-07-01 | 2016-07-01 | 2016-07-01 | 22682800 | Completed
2 | Proposed parking and ablution block for Wangige egg shed | Kabete | Kabete | 2016-05-01 | 2016-06-01 | 2016-06-01 | 393671000 | Completed
3 | Proposed construction of an egg shed at Wangige market | Kabete | Kabete | 2016-04-01 | 2016-06-01 | 2016-06-01 | 5485582 | Completed
FY 2016/2017
4 | Proposed construction of Limuru market | Limuru | Limuru Central | 2016-08-01 | 2020-05-01 | 2020-05-01 | 45947905 | Completed
FY 2017/2018
5 | Proposed construction of a Market at Kamwangi | Gatundu North | Githobokoni | 2017-07-01 | 2020-06-01 | 2020-06-01 | 33696745 | Completed
6 | Proposed construction of Limuru Hawkers market | Limuru | Limuru Central | 2017-11-01 | 2018-06-01 | 2018-08-01 | 17893735 | Completed
FY 2018/2019
7 | Proposed fencing works at Ngoliba market | Thika | Ngoliba | 2018-07-01 | 2018-08-01 | 2018-08-01 | 3150400 | Completed
FY 2019/2020
8 | Gatundu Market Roof Repairs | Gatundu South | Ngenda | 2019-12-01 | 2020-03-01 | 2020-03-01 | 4934428.43 | Completed
9 | Proposed construction of a boda boda shed at Kagaa shopping centre | Lari | Kamburu | 2019-08-01 | 2019-09-01 | 2019-09-01 | 499190 | Completed
FY 2020/2021
10 | Proposed construction of an ablution block and offices for Juja Farm Market | Juja | Kalimoni | 2020-07-01 | 2020-10-01 | 2020-10-01 | 4782679 | Completed
11 | Proposed construction of an ablution block and offices for Kimunyu Market | Gatundu South | Ngenda | 2020-07-01 | 2020-12-01 | 2020-12-01 | 3791629.2 | Completed
12 | Proposed construction of an ablution block and offices for Kerwa Market | Kikuyu | Sigona | 2020-07-01 | 2020-12-01 | 2020-12-01 | 3886473.2 | Completed
13 | Proposed construction of a boda boda shed at Muchatha | Kiambaa | Muchatha | 2020-08-01 | 2020-09-01 | 2020-09-01 | 499675 | Completed
14 | Proposed construction of a boda boda shed at Kanyariri, Gitaru | Kabete | Gitaru | 2020-08-01 | 2020-09-01 | 2020-09-01 | 499675 | Completed
15 | Proposed construction of a boda boda shed at Gitwe | Githunguri | Ndarugu | 2020-08-01 | 2020-09-01 | 2020-09-01 | 495550 | Completed
FY 2021/2022
16 | Proposed construction of a boda boda shed at Kimende | Lari | Kijabe | 2022-07-01 | 2022-12-01 | 2022-12-01 | 493240 | Completed
17 | Proposed construction of a modern boda boda shed at Juja farm | Juja | Kalimoni | 2022-07-01 | 2022-12-01 | 2022-12-01 | 776640 | Completed
18 | Proposed construction of a modern boda boda shed at Riabai Shopping Centre | Kiambu | Riabai | 2022-01-01 | 2022-03-01 | 2022-03-01 | 794900 | Completed
19 | Proposed construction of a modern boda boda shed at Kiganjo Kona 1 | Thika | Kamenu | 2022-01-01 | 2022-03-01 | 2022-03-01 | 776860 | Completed
20 | Proposed construction of a modern boda boda shed at Gituamba ward | Gatundu North | Gitumba | 2022-01-01 | 2022-03-01 | 2022-03-01 | 777450 | Completed
21 | Proposed construction of a modern boda boda shed at Juja Kalimoni | Juja | Kalimoni | 2021-07-01 | 2021-08-01 | 2021-08-01 | 776640 | Completed
22 | Proposed Construction of Kiganjo Market | Gatundu South | Kiganjo | 2021-12-01 | 2022-06-01 | 2022-06-01 | 24377710 | Completed
23 | Construction of Gitaru market | Kabete | Gitaru | 2021-07-01 | 2022-06-01 | 2023-09-01 | 22912210 | Completed
FY 2022/2023
24 | Proposed Construction Kigumo Market Phase 1 | Githunguri | Komothai | 2022-05-01 | 2022-12-01 | 2022-12-01 | 37791102.79 | Completed
25 | Proposed Construction of public washrooms and landscaping in Kwa Mathore view point | Lari | Lari/Kirenga | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2600000 | Completed
FY 2023/2024
26 | Proposed Phase 1 Temporary Market: Ground Preparation and Ablution Block at Kiandutu | Thika | Thika township | 2024-04-01 | 2024-06-01 | 2024-06-01 | 4985465 | Completed
27 | Proposed Construction of Masonry Perimeter Wall for Kiandutu | Thika | Thika township | 2024-04-01 | 2024-06-01 | 2024-06-01 | 4993980 | Completed
28 | Proposed Construction of Underground Water Tank, Rehabilitation of a Perimeter Wall, Construction of Office and Guard House and Egg Shade at Gitaru Market | Kabete | Gitaru | 2024-01-01 | 2024-02-01 | 2024-02-01 | 4975420 | Completed
29 | Proposed Construction of County Aggregation and Industrial Park At Waruhiu Farm | Githunguri | Ngewa | 2024-04-01 |  |  | 498828815 | Ongoing
30 | Proposed construction of Rironi Phase II Market | Limuru | Limuru Central | 2023-10-01 | 2024-04-01 | 2024-04-01 | 18753870 | Completed
31 | Proposed construction of Modern Kiosks in Kabete | Kabete | Kabete | 2023-11-01 | 2024-12-01 | 2025-06-01 | 9257525 | Completed
FY 2024/2025
32 | Proposed construction of Kagwe Market | Lari | Nyanduma | 2024-06-01 | 2025-04-01 |  | 49108200 | Ongoing
33 | Proposed construction of Lussigetti Market | Kikuyu | Nachu | 2024-06-01 | 2025-03-01 |  | 34895325 | Ongoing
34 | Proposed construction of Kinoo Market | Kikuyu | Kinoo | 2024-06-01 | 2025-04-01 |  | 48098413 | Ongoing
35 | Proposed construction of Kimbo Matangiini Market | Juja | Theta | 2024-06-01 | 2025-04-01 |  | 36600000 | Ongoing
36 | Proposed construction of Dagoretti Market | Kikuyu | Kikuyu | 2024-08-01 | 2025-07-01 |  | 49346560 | Ongoing
37 | Proposed construction of Ndeiya Market | Limuru | Ndeiya | 2024-09-01 | 2026-06-01 |  | 21016620 | Ongoing
38 | Proposed construction of Gituamba Market | Lari | Gituamba | 2024-09-01 | 2025-09-01 |  | 20333755 | Ongoing
39 | Proposed construction of Karuri market | Kiambaa | Karuri | 2024-07-01 | 2025-06-01 |  | 50000000 | Ongoing
40 | Proposed construction of Gakoe market | Gatundu North | Githobokoni | 2024-07-01 | 2025-06-01 |  | 29146310 | Ongoing
41 | Proposed Construction of Kamangu Market shed | Kikuyu | Nachu | 2024-07-01 | 2025-06-01 | 2025-06-01 | 29797260 | Completed
42 | Proposed Construction of Maguguni Market shed | Thika | Ngoliba | 2024-07-01 | 2025-06-01 |  | 34967025 | Ongoing
43 | Proposed Construction of Mataara Market | Gatundu North | Githobokoni | 2024-07-01 | 2025-06-01 |  | 29955690 | Ongoing
44 | Construction of boda boda sheds | All subcounties | All wards | 2024-07-01 | 2025-06-01 |  | 22050000 | Ongoing
45 | Fabrication of 180 No. of Bodaboda Sheds phase II (90 N0.) | All subcounties | All wards | 2024-07-01 | 2025-06-01 |  | 46400000 | Ongoing
HEALTH SERVICES
FY 2013/14
1 | Proposed construction of outpatient Dept at Igegania Sub County district hospital (phase I) | Gatundu North | Mang'u | 2013-04-01 | 2013-11-01 | 2023-11-01 | 21195486.5 | Complete
2 | Proposed maternity ward at Kiambu district hospital | Kiambu | Kiambu Township | 2013-07-01 | 2013-12-01 | 2013-12-01 | 2218216 | Complete
3 | Proposed renovations, alterations to maternity block at Kihara hospital | Kiambaa | Kihara | 2013-11-01 | 2014-01-01 | 2014-01-01 | 1030700 | Complete
4 | Refurbishment And Renovation Of Building Works For Gatuanyaga Health Centre In Thika Sub County, Kiambu County | Thika | Gatuanyaga | 2013 | 2014 | 2014 | 926282 | Complete
5 | Proposed model Health Centre at Wangige Hospital | Kabete | Kabete | 2013-03-01 | 2013-06-01 | 2013-06-01 | 4984255 | Complete
FY 2014/15
6 | Proposed refurbishment of Wangige Health Centre | Kabete | Kabete | 2014-06-01 | 2014-08-01 | 2014-08-01 | 787500 | Complete
7 | Proposed refurbishment: Nyayo wards-female wing at Kiambu hospital | Kiambu | Kiambu Township | 2014-07-01 | 2015-07-01 | 2015-07-01 | 2895720 | Complete
8 | Proposed renovations and tiling of the maternity block at Karuri health centre | Kiambaa | Karuri | 2014-01-01 | 2014-03-01 | 2014-03-01 | 367900 | Complete
9 | Proposed conversion of old theatre to surgical ward at Gatundu hospital | Gatundu South | Ng'enda | 2014-01-01 | 2014-03-01 | 2014-03-01 | 2313735 | Complete
10 | Proposed Expansion of MCH/OPD at Juja Farm Health centre | Juja | Kalimoni | 2015-01-01 | 2016-11-01 | 2016-11-01 | 2495759 | Complete
11 | Proposed construcion of a perimeter wall at Thika level V HOSPITAL | Thika | Hospital | 2014 | 2014-05-01 | 2014-05-01 | 2993700 | Complete
12 | Proposed Expansion Mch/OpdAtKiandutu Health Centre | Thika | Thika township | 2015-01-01 | 2016-11-01 | 2016-11-01 | 2477820 | Complete
13 | Proposed Expansion of MCH/OPD at Munyu Health Center | Thika | Gatuanyaga | 2015-01-01 | 2016-11-01 | 2016-11-01 | 2503571 | Complete
14 | Proposed refurbishment and renovation of Ndula Health Centre | Thika | Ngoliba | 2014 | 2015 | 2015 | 1108500 | Complete
15 | Proposed construction and renovation works; rain water harvesting at Langata dispensary Ruiru county | Ruiru | Kiuu | 2014-05-01 | 2015-03-01 | 2015-03-01 | 562250 | Complete
FY 2015/16
16 | Proposed installation of 100 KVA generator set c/w associated works to Githunguri Health Centre | Githunguri | Githunguri | 2015-05-01 | 2015-07-01 | 2015-07-01 | 3980000 | Complete
17 | Proposed access roads and parking at Kiambu hospital | Kiambu | Kiambu Township | 2015-06-01 | 2015-09-01 | 2015-09-01 | 7137240 | Complete
18 | Proposed construction and renovation work covered walkways at Kiambu hospital | Kiambu | Kiambu Township | 2015-05-01 | 2016-06-01 | 2016-06-01 | 4000200 | Complete
19 | Proposed construction and renovation work of maternity “B” at Kiambu hospital | Kiambu | Kiambu Township | 2015-05-01 | 2016-06-01 | 2016-06-01 | 3139700 | Complete
20 | Proposed construction and renovation work; OPD at Kiambu hospital | Kiambu | Kiambu Township | 2015-05-01 | 2016-02-01 | 2016-02-01 | 2992325 | Complete
21 | Proposed CEC’S office upgrading and refurbishment at Kiambu hospital | Kiambu | Kiambu Township | 2015-05-01 | 2015-06-01 | 2015-06-01 | 247400 | Complete
22 | Proposed refurbishment of occupational therapy block at Kiambu hospital | Kiambu | Kiambu Township | 2015-07-01 | 2015-11-01 | 2015-11-01 | 450000 | Complete
23 | Proposed refurbishment; CME room at Kiambu hospital | Kiambu | Kiambu Township | 2015-07-01 | 2015-11-01 | 2015-11-01 | 450000 | Complete
24 | Proposed repainting works at Kiambu hospital | Kiambu | Kiambu Township | 2015-07-01 | 2015-12-01 | 2015-12-01 | 2796070 | Complete
25 | Proposed renovations and refurbishment at Ruiru sub-district hospital | Ruiru | Biashara | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1200730 | Complete
26 | Proposed installation of a 100KUA generator set C/W associated works to Ruiru sub-district hospital | Ruiru | Biashara | 2015-01-01 | 2015-07-01 | 2015-07-01 | 3980000 | Complete
27 | Proposed re-roofing works at Ruiru sub-district hospital | Ruiru | Biashara | 2015-07-01 | 2016-02-01 | 2016-02-01 | 2165400 | Complete
28 | Proposed conversion and renovation of male ward at Ruiru sub-county hospital | Ruiru | Biashara | 2015-07-01 | 2016-02-01 | 2016-02-01 | 731063 | Complete
29 | Proposed construction of a perimeter fence at Gatundu sub-district hospital | Gatundu South | Ng'enda | 2015 | 2018-10-01 | 2018-10-01 | 16892850 | Complete
30 | Proposed health centre (container pre-fab type) at Muchatha dispensary | Kiambaa | Muchatha | 2015-07-01 | 2016-11-01 | 2016-11-01 | 2488320 | Complete
31 | Proposed installation of 100 KVA generator set s/w associated works at Githunguri health centre | Githunguri | Githunguri | 2015-01-01 | 2015-07-01 | 2015-07-01 | 3980000 | Complete
32 | Proposed laboratory and dental unit at Thika level (v) hospital | Thika | Hospital | 2015-01-01 | 2017-06-01 | 2017-06-01 | 31486396 | Complete
33 | Renovations and refurbishment of maternity theatre and associated works at Igegania hospital | Gatundu North | Mang'u | 2015-01-01 | 2016-06-01 | 2016-06-01 | 2907010 | Complete
34 | Proposed expansion of MCH/OPD at Mbichi health centre | Gatundu North | Mang'u | 2015-01-01 | 2016-11-01 | 2016-11-01 | 3352600 | Complete
35 | Proposed expansion of MCH/OPD at Ngorongo health centre | Gatundu North | Chania | 2015-01-01 | 2016-11-01 | 2016-11-01 | 3336400 | Complete
36 | Proposed rehabilitation works at Kiribaribi dispensary | Thika | Thika township | 2015-01-01 | 2016-06-01 | 2016-06-01 | 840142 | Complete
37 | Proposed refurbishment of Gitare health centre | Gatundu South | Kiganjo | 2015-01-01 | 2016-06-01 | 2016-06-01 | 2441120 | Complete
38 | Proposed refurbishment and renovation of Munyu dispensary | Thika | Gatuanyaga | 2015-01-01 | 2016-05-01 | 2016-05-01 | 1680479 | Complete
39 | Proposed rehabilitation of Karatu health centre (Surgical theatre) | Gatundu South | Ndarugo | 2015-01-01 | 2016-04-01 | 2016-04-01 | 4206170 | Complete
40 | Expansion of OPD/MCH at kiandutu Health Centre | Thika | Thika township | 2015-01-01 | 2015-11-01 | 2015-11-01 | 2477820 | Complete
41 | Proposed expansion of MCH/OPD at Juja Farm Health Centre | Juja | Kalimoni | 2015-01-01 | 2015-11-01 | 2015-11-01 | 2495759 | Complete
42 | Proposed expansion of Mutate Health Centre | Gatundu South | Kiamwangi | 2015-01-01 | 2015-08-01 | 2015-08-01 | 2440790 | Complete
43 | Proposed expansion of MCH/OPD at Munyu Farm Health Centre | Thika | Gatuanyaga | 2015-01-01 | 2015-12-01 | 2015-12-01 | 2503571 | Complete
44 | Proposed refurbishment and renovation of Ndula Health Centre | Thika | Ngoliba | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1108500 | Complete
45 | Proposed rehabilitation & refurbishment of Ng’enda Health Centre | Gatundu south | Kiamwangi | 2015-01-01 | 2015-06-01 | 2015-06-01 | 2414570 | Complete
46 | Proposed refurbishment and renovation of Munyu dispensary | Thika | Ngoliba | 2015-01-01 | 2016-05-01 | 2016-05-01 | 1680479 | Complete
47 | Refurbishment and Renovation of Igegania District Hospital | Gatundu North | Mang'u | 2015-01-01 | 2016-05-01 | 2016-05-01 | 2909295 | Complete
48 | Rehabilitation and Refurbishment Works At Karibaribi Dispensary | Thika | Thika township | 2015-01-01 | 2016-05-01 | 2016-05-01 | 840142 | Complete
49 | Proposed expansion of MCH/OPD at Ngorongo health centre | Gatundu North , | Chania | 2015-01-01 | 2016-05-01 | 2016-05-01 | 3336400 | Complete
50 | Proposed refurbishment of Muthara Health | Juja | Witeithie | 2015-01-01 | 2016-05-01 | 2016-05-01 | 2919300 | Complete
51 | Proposed Expansion of Mch/OpdatMbichi Dispensary | Gatundu North | Mang'u | 2015-01-01 | 2016-05-01 | 2016-05-01 | 3352600 | Complete
52 | Refurbishment and Renovation of Munyu Health Centre | Thika | Gatuanyaga | 2015-01-01 | 2016-05-01 | 2016-05-01 | 1680479 | Complete
53 | Proposed Works at Kireita Dispensary | Lari | Kijabe | 2015-01-01 | 2015-11-01 | 2015-11-01 | 2,529.040.00 | Complete
54 | Proposed Works at Kagaa Dispensary | Lari | Kamburu | 2015-01-01 | 2015-11-01 | 2015-11-01 | 2596800 | Complete
55 | Proposed expansion of MCH/OPD at Mutati health centre | Gatundu South | Kiamwangi | 2015-01-01 | 2015-11-01 | 2015-11-01 | 3255350 | Complete
56 | Proposed construction of 4 storeyed type medical ward block at Tigoni Level 4 Hospital | Limuru | Tigoni/Ngecha | 2015-07-01 | 2025-06-01 | 2025-06-01 | 170595604.08 | Partly in use
57 | Proposed construction of 4 storeyed type medical ward block at Lari Sub – District Hospital | Lari | Lari/Kirenga | 2015-07-01 | 2026-06-01 | 2026-06-01 | 191807805 | Ongoing
58 | Proposed construction of 4 storeyed type medical ward block at Wangige Level 4 Hospital | Kabete | Kabete | 2015-07-01 | 2025-06-01 | 2025-06-01 | 270725815 | Partly in use
FY 2016/17
59 | Proposed re-roofing works: maternity B at Kiambu hospital | Kiambu | Kiambu Township | 2016-01-01 | 2016-06-01 | 2016-06-01 | 2372180 | Complete
60 | Proposed landscaping works at Kigumo health centre | Githunguri | Komothai | 2016-12-01 | 2017-02-01 | 2017-02-01 | 1349100 | Complete
61 | Proposed completion of Kaibere dispensary | Gatundu North | Githobokoni | 2016-07-01 | 2017-02-01 | 2017-02-01 | 3998480 | Complete
62 | Proposed refurbishment water tank and base 8 number door pit latrine at Mbari-ya-igi dispensary | Githunguri | Komothai | 2016-07-01 | 2016-12-01 | 2016-12-01 | 3661490 | Complete
63 | Proposed extension and refurbishment at Mundoro dispensary | Gatundu South | Ndarugo | 2016-07-01 | 2017-03-01 | 2017-03-01 | 3993585 | Complete
64 | Proposed incinerator housing at Githunguri health centre | Githunguri | Githunguri | 2016-03-01 | 2018-06-01 | 2018-06-01 | 1426820 | Complete
65 | Proposed Construction of Reproductive Health Unit at Thika Level V Hospital | Thika | Hospital | 2016-07-01 | 2018-04-01 | 2018-04-01 | 667395434.2 | Complete
66 | Proposed Refurbishment to Nyayo Wards Male Wing at Kiambu District Hospital | Kiambu | Kiambu Township | 2016-07-01 | 2017-06-01 | 2017-06-01 | 4188356.2 | Complete
67 | Proposed works at Gatuanyaga Dispensary | Thika | Gatuanyaga | 2016-07-01 | 2017-06-01 | 2017-06-01 | 3049390 | Complete
68 | Proposed rehabilitation and refurbishment of ha-mundia health centre | Juja | Murera | 2016-07-01 | 2017-06-01 | 2017-06-01 | 3183880 | Complete
69 | Proposed Refurbishment to Nyayo Wards - Male Wing (Phase II) at Kiambu District Hospital | Kiambu | Kiambu Township | 2016-07-01 | 2018-06-01 | 2018-06-01 | 3306420 | Complete
70 | Proposed construction of maternity block at Gatuanyaga dispensary | Thika | Gatuanyaga | 2016-07-01 | 2017-06-01 | 2017-06-01 | 3741790 | Complete
71 | Proposed Kitchen at Gatuanyaga Dispensary | Thika | Gatuanyaga | 2016-07-01 | 2017-06-01 | 2017-06-01 | 2245870 | Complete
FY 2017/18
72 | Proposed refurbishment to Nyayo wards-female wing at Kiambu hospital (phase II) | Kiambu | Kiambu Township | 2017-07-01 | 2018-03-01 | 2018-03-01 | 3996420 | Complete
73 | Paint works and general renovation at Gatundu hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 2985080 | Complete
74 | Proposed external works at Gatundu level (iv) hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3976110 | Complete
75 | Proposed refurbishment, water tank and tank base and construction of 8no. pit latrine ablution bloc at Mbari -yaIgi Dispensary | Githunguri | Komothai | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3661490 | Complete
76 | Proposed refurbishment at Limuru health centre | Limuru | Limuru Central | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3822331 | Complete
77 | Proposed re-roofing works at Gatundu level (iv) hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3989900 | Complete
78 | Proposed walkways at Gatundu level (iv) hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3993350 | Complete
79 | Supply and installation of curtain rails, curtain clothes and bed screens for Gatundu hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 1998000 | Complete
80 | Proposed dis-installation, delivery to site of a generator set to Tigoni hospital and re-installation | Limuru | Tigoni/Ngecha | 2017-02-01 | 2017-04-01 | 2017-04-01 | 2115000 | Complete
81 | Proposed internal renovations at Gatundu level (iv) hospital | Gatundu South | Ng'enda | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3968400 | Complete
82 | Proposed renovation works to Kihara hospital | Kiambaa | Kihara | 2017-07-01 | 2018-02-01 | 2018-02-01 | 3975760 | Complete
83 | Proposed construction of surgical Theatre at Lari Hospital | Lari | Lari/Kirenga | 2017-07-01 | 2017-11-01 | 2017-11-01 | 11411670 | Complete
84 | Proposed refurbishment at Limuru health centre | Limuru | Limuru Central | 2017-07-01 | 2017-11-01 | 2017-11-01 | 3822331 | Complete
85 | Proposed works at Gatuanyaga dispensary | Thika | Gatuanyaga | 2017-01-01 | 2017-03-01 | 2017-03-01 | 3049390 | Complete
86 | Proposed rehabilitation and refurbishment of ha-mundia health centre | Juja | Murera | 2017-01-01 | 2017-03-01 | 2017-03-01 | 3183880 | Complete
87 | Proposed construction of maternity block at Gatuanyaga dispensary | Thika | Gatuanyaga | 2017-01-01 | 2017-03-01 | 2017-03-01 | 3741790 | Complete
88 | Proposed refurbishment works and fencing at Maguguni health centre | Thika | Ngoliba | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3395760 | Complete
89 | Proposed renovation of existing facilities and completion of maternity ward at Athi dispensary | Juja | Kalimoni | 2018-01-01 | 2018-08-01 | 2018-08-01 | 3799360 | Complete
90 | Proposed erection and completion of covered walkways at Lussingetti sub-district hospital | Kikuyu | Nachu | 2018-01-01 | 2018-05-01 | 2018-05-01 | 2510198 | Complete
91 | Proposed construction of perimeter fence at Gikambura health centre | Kikuyu | Karai | 2018-01-01 | 2018-06-01 | 2018-06-01 | 3802970 | Complete
92 | Proposed refurbishment and chain link fencing at Kinoo dispensary | Kikuyu | Kinoo | 2018-01-01 | 2018-06-01 | 2018-06-01 | 1520600 | Complete
93 | Proposed refurbishment to Gikambura health centre | Kikuyu | Karai | 2018-01-01 | 2018-06-01 | 2018-06-01 | 1490315 | Complete
94 | Proposed refurbishment and completion work at Ngeteti dispensary | Githunguri | Githunguri | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3374650 | Complete
95 | Proposed fencing at Ngeteti dispensary | Githunguri | Githunguri | 2018-01-01 | 2018-05-01 | 2018-05-01 | 1681740 | Complete
96 | Proposed perimeter fencing at Githunguri-ruiru health centre | Ruiru | Biashara | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3153710 | Complete
97 | Proposed ablution block at Gichuru dispensary | Kikuyu | Sigona | 2018-01-01 | 2018-05-01 | 2018-05-01 | 2512330 | Complete
98 | Proposed completion works and fencing at Uplands dispensary | Lari | Lari/Kirenga | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3314650 | Complete
99 | Proposed fencing at Athi dispensary | Juja | Kalimoni | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3118350 | Complete
100 | Proposed perimeter fencing at Githunguri-ruiru health centre | Ruiru | Biashara | 2018-01-01 | 2018-05-01 | 2018-05-01 | 3153710 | Complete
101 | Proposed erection and completion of covered walkways at Lari sub-county hospital | Lari | Lari/Kirenga | 2018-01-01 | 2018-05-01 | 2018-05-01 | 1593940 | Complete
102 | Proposed refurbishment at Karai muslim dispensary | Kikuyu | Karai | 2018-01-01 | 2018-05-01 | 2018-05-01 | 1706150 | Complete
FY 2018/19
103 | Proposed construction of surgical theatre at Lussigetti health centre | Kikuyu | Nachu | 2018-07-01 | 2019-05-01 | 2019-05-01 | 11434380 | Complete
104 | Proposed health centre (container pre-fab type) at Kagwee, Kiambu | Lari | Nyanduma | 2018-07-01 | 2018-12-01 | 2018-12-01 | 2469984 | Complete
105 | Proposed ablution block at Thigio health centre | Limuru | Ndeiya | 2018-07-01 | 2018-08-01 | 2018-08-01 | 1490315 | Complete
106 | Proposed refurbishment works and completion of maternity ward at Githunguri health centre-Ruiru | Ruiru | Biashara | 2019-01-01 | 2019-05-01 | 2019-05-01 | 3076095 | Complete
107 | Renovations and completion of Athi dispensary | Juja | Kalimoni | 2019-01-01 | 2019-05-01 | 2019-05-01 | 3797960 | Complete
108 | Proposed construction of a toilet block at Uplands dispensary | Lari | Lari/Kirenga | 2019-01-01 | 2019-06-01 | 2019-06-01 | 2486970 | Complete
109 | Proposed refurbishment works for Karura Ka Nyungu dispensary | Kiambaa | Nyathuna | 2019-01-01 | 2019-06-01 | 2019-06-01 | 2865580 | Complete
110 | Proposed Mutonya dispensary renovation works | Ruiru | Gatong'ora | 2018-12-01 | 2019-04-01 | 2019-04-01 | 3937250 | Complete
FY 2019/20
111 | Proposed renovations in administration offices and storage shelves for Kiambu level V hospital | Kiambu | Kiambu Township | 2019-07-01 | 2020-03-01 | 2020-03-01 | 3989606.33 | Complete
112 | Proposed renovations to Karibaribi dispensary laboratory | Thika | Thika Township | 2019-06-01 | 2019-07-01 | 2019-07-01 | 198920 | Complete
113 | Proposed repair replacement and installation of electrical equipment and accessories at Karatu health centre | Gatundu South | Ndarugo | 2019-10-01 | 2019-11-01 | 2019-11-01 | 479150 | Complete
114 | Proposed refurbishment and renovation to OPD at Ruiru sub-county hospital | Ruiru | Biashara | 2019-07-01 | 2019-12-01 | 2019-12-01 | 944900 | Complete
115 | Proposed construction of two number doors and urinal pit latrine at Ndenderu dispensary | Kiambaa | Ndenderu | 2019-09-01 | 2019-12-01 | 2019-12-01 | 350635 | Complete
116 | Proposed fencing works at Kamburu dispensary | Kamburu | Kamburu | 2019-07-01 | 2019-08-01 | 2019-08-01 | 3662950 | Complete
117 | Proposed repair replacement and installation of electrical equipment and accessories at Karatu health centre | Gatundu South | Ndarugo | 2019-10-01 | 2019-11-01 | 2019-11-01 | 479150 | Complete
118 | Proposed Renovation Works at the administration Office and Storage facilities at KL5 Hospital | Kiambu | Kiambu Township | 2019-11-01 | 2020-02-01 | 2020-02-01 | 3989806 | Complete
119 | Proposed renovations for laundry room at Gatundu hospital | Gatundu South | Ng'enda | 2020-04-01 | 2020-08-01 | 2020-08-01 | 1980453.6 | Complete
120 | Proposed Quarantine Zone (Phase II) for Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-04-01 | 2020-06-01 | 2020-06-01 | 4400000 | Complete
121 | Proposed Isolation Centre at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-04-01 | 2020-05-01 | 2020-05-01 | 4192230 | Complete
122 | Proposed Chainlink at GithigaCemetry | Githunguri | Githiga | 2020-04-01 | 2020-06-01 | 2020-06-01 | 3451425 | Complete
123 | Proposed Construction of Body Viewing Shed and Toilet Block at GithigaCemetry | Githunguri | Githiga | 2020-04-01 | 2020-06-01 | 2020-06-01 | 2634810 | Complete
FY 2020/21
124 | Proposed 2000L solar water heating system at Gatundu level (v) hospital laundry | Gatundu South | Ng'enda | 2020-07-01 | 2020-08-01 | 2020-08-01 | 2629800 | Complete
125 | Renovation and Conversion of old maternity block to a Covid 19 Isolation Ward at Thika Level V Hospital | Thika | Hospital | 2020-05-01 | 2020-11-01 | 2020-11-01 | 3879450 | Complete
126 | Proposed Renovation works at General Kago Mortuary in Thika Level 5 Hospital | Thika | Hospital | 2020 | 2021 | 2021 | 3720650 | Complete
127 | Proposed Renovations to Kiambu Level 5 Hospital ICU unit for Covid -19 Isolation Unit | Kiambu | Kiambu Township | 2020-07-01 | 2021-02-01 | 2021-02-01 | 3958600 | Complete
128 | Proposed Mechanical Works for the Proposed Extension to ICU at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-07-01 | 2021-02-01 | 2021-02-01 | 3381560 | Complete
129 | Proposed Electrical Works for the Proposed Extension to ICU at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-07-01 | 2021-02-01 | 2021-02-01 | 2417400 | Complete
130 | Proposed Isolation Centre InRuiru Hospital | Ruiru | Biashara | 2020-09-01 | 2021-06-01 | 2021-06-01 | 61084950 | Complete
131 | Proposed Rehabilitation of Morgue at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-11-01 | 2021-01-01 | 2021-01-01 | 3999975 | Complete
132 | Proposed Renovations and Alterations for Maternity Theatre at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-12-01 | 2021-02-01 | 2021-02-01 | 3785340 | Complete
133 | Proposed Renovation Works at New Born Unit at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2020-10-01 | 2020-11-01 | 2020-11-01 | 499260 | Complete
134 | Proposed Renovations of Doctor’s House and store at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2021-04-01 | 2021-05-01 | 2021-05-01 | 3096180 | Complete
135 | Proposed Clearing of the Dumpsite and Excavation behind the pediatric ward at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2021-01-01 | 2021-02-01 | 2021-02-01 | 2575000 | Complete
136 | Proposed Chain link fencing at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2021-02-01 | 2021-04-01 | 2021-04-01 | 3962550 | Complete
FY 2021/22
137 | Proposed supply, installation, testing and commissioning of electrical works to theatre and OPD blocks at Ruiru sub-county hospital | Ruiru | Biashara | 2021-07-01 | 2021-09-01 |  | 998400 | Complete
138 | Proposed Parking, Driveways and and facelifting of Ruiru Level IV Hospital | Ruiru | Biashara | 2021-11-01 | 2021-12-01 |  | 15563750 | Complete
139 | Proposed supply, installation, testing and commissioning of electrical works to theatre and OPD blocks at Ruiru sub-county hospital | Ruiru | Biashara | 2021-07-01 | 2021-09-01 |  | 998400 | Complete
140 | Proposed Covered Walkways for the Isolation Centre in Ruiru Hospital | Ruiru | Biashara | 2021-06-01 | 2021-09-01 |  | 4273600 | Complete
141 | Proposed Repainting and Renovations at Kiambu Level 5 Hospital | Kiambu | Kiambu Township | 2021-06-01 | 2021-07-01 |  | 2997570 | Complete
142 | Proposed refurbishment and renovations at Kihara level (iv) hospital | Kiambaa | Kihara | 2022-01-01 | 2022-05-01 |  | 1931920 | Complete
FY 2022/23
143 | Proposed Construction of Perimeter Wall at Gachororo Health Center | Juja | Juja | 2022-07-01 | 2022-11-01 |  | 13331380 | Complete
144 | Proposed Central Medical Store in Ruiru level IV Hospital | Ruiru | Biashara | 2022-01-01 | 2024-08-01 |  | 41973140 | 99% Complete
145 | Proposed Construction of isolation Centre in Lusiggetti Hospital | Kikuyu | Nachu | 2022-07-01 | 2023-04-01 |  | 37967210 | Complete
146 | Proposed construction of a new placenta pit at Ruiru level (iv) hospital in Kiambu county | Ruiru | Biashara | 2023-04-01 | 2023-06-01 |  | 276813 | Complete
FY 2023/24
147 | Proposed construction of a typical ward, medical ward block at Karuri level (iv) hospital | Kiambaa | Karuri | 2023-10-01 | 2025-04-01 |  | 180734625.3 | Ongoing
148 | Proposed Completion of Ground, 1st and 2nd floors at Kikuyu level iv Hospital | Kikuyu | Kikuyu | 2023-04-01 | 2025-04-01 |  | 157304215 | Ongoing
149 | Proposed Refurbishments at Nyathuna Level iv Hospital | Kabete | Nyathuna | 2023-09-01 | 2024-12-01 |  | 16250050 | Ongoing
150 | Proposed Level III Hospital in Kahawa Sukari | Ruiru | Kahawa Sukari | 2023-09-01 | 2024-10-01 |  | 43813600 | Ongoing
151 | Proposed Level III Hospital in Wangunyu, Ndenderu | Kiambaa | Ndenderu | 2023-12-01 | 2024-11-01 |  | 44112284 | Ongoing
152 | Proposed Level III Hospital in Gathiga | Kabete | Nyathuna | 2023-05-01 | 2026-05-01 |  | 60690500 | Ongoing
153 | Proposed Completion Works of Gatundu Morgue | Gatundu South | Ng'enda | 2023-01-01 | 2025-01-01 |  | 57327899.59 | Ongoing
154 | Proposed Gitaru level III Hospital | Kabete | Gitaru | 2023-10-01 | 2025-10-01 |  | 42600000 | Ongoing
155 | Proposed Inpatient Wing Hospital at Ndeiya | Limuru | Ndeiya | 2023-05-01 | 2026-05-01 |  | 42965100 | Ongoing
156 | Proposed Juja level IV Hospital (Gachororo) | Juja | Juja | 2023-10-01 | 2025-10-01 |  | 196899815 | Ongoing
157 | Renovation of Kihara Hospital Phase 1 | Kiambaa | Kihara | 2023-11-01 | 2024-10-01 |  | 18657050 | Complete
158 | Renovation of Karuri Hospital | Kiambaa | Karuri | 2023-12-01 | 2024-09-01 |  | 8442540 | Complete
159 | Proposed electrical repair works at Tigoni level (iv) hospital | Limuru | Tigoni/Ngecha | 2024-04-01 | 2024-06-01 |  | 2579378.4 | Complete
160 | Proposed renovations to one number hospital, two number bedroom hostel at Tigoni hospital | Limuru | Tigoni/Ngecha | 2024-05-01 | 2024-06-01 |  | 372500 | Complete
161 | Proposed construction of Uthiru Level III Hospital | Kabete | Uthiru | 2024-05-01 | 2026-05-01 |  | 64640607.39 | Ongoing
162 | Proposed Facelift and Renovation works at Ngorongo Health Centre | Gatundu North | Chania | 2024-02-01 | 2024-05-01 |  | 4596030 | Complete
163 | Proposed Renovation to Mugutha Dispensary - Opd Block | Juja | Murera | 2024-02-01 | 2024-05-01 |  | 2797920 | Ongoing
164 | Proposed Renovations / Facelifting at Gituamba Health Facility | Gatundu North | Gituamba | 2024-04-01 | 2024-07-01 |  | 4180475 | Complete
165 | Proposed Construction of Storey Level 3 Health Facility at Kiganjo | Thika | Kamenu | 2024-06-01 | 2025-01-01 |  | 57762360 | Ongoing
166 | Proposed Renovations of Ngoliba Health Centre | Thika | Ngoliba | 2024-04-01 | 2025-04-01 |  | 3634700 | Ongoing
167 | Proposed Level III Hospital in Kiawaroga | Limuru | Limuru East | 2024-02-01 | 2026-02-01 |  | 43525200 | Ongoing
168 | Proposed Perimeter wall in Ruiru level IV Hospital | Ruiru | Biashara | 2024-01-01 | 2024-03-01 |  | 12183714 | Ongoing
169 | Proposed Perimeter wall Makwa health centre | Gatundu North | Mang'u | 2024-05-01 | 2025-12-01 |  | 6642120 | Complete
170 | Proposed Rehabilitation Works at Gachika Dispensary, Gatundu South Subcounty | Gatundu South | Kiganjo | 2024-05-01 | 2024-11-01 |  | 9998230 | Complete
171 | Proposed Level III Hospital in Ndumberi | Kiambu | Ndumberi | 2023-10-01 | 2025-10-01 |  | 41913760 | Ongoing
FY 2024/25
172 | Proposed Renovations / Facelifting at Gachege Health Facility | Gatundu North | Githobokoni | 2024-10-01 | 2025-01-01 |  | 4140133 | Ongoing
173 | Proposed Construction of Vertical Extension ramp, sentry box, driveways parking and walkways from OPD to IPD Block at Igegania Level IV Hospital | Gatundu North | Ng'enda | 2024-10-01 | 2025-10-01 |  | 29640000 | Ongoing
174 | Proposed Level III Hospital at Gichuru Zambezi Health Centre | Kikuyu | Sigona | 2024-09-01 | 2026-09-01 |  | 57984940 | Ongoing
175 | Construction of Ndeiya level III Hospital | Limuru | Ndeiya | 2024-08-01 | 2025-06-01 |  | 42965100 | Ongoing
176 | Construction of Gathiga level III Hospital | Kabete | Nyathuna | 2024-08-01 | 2025-06-01 |  | 60690500 | Ongoing
177 | Completion of Bibirioni level 4 hospital | Limuru | Bibirioni | 2025-04-01 | 2027-12-01 |  | 224603050 | Ongoing
178 | Construction of Gathanje level II hospital | Githunguri | Ikinu | 2025-03-01 | 2027-03-01 |  | 13382880 | Ongoing
179 | Construction of ablution block at Kagwe dispensary | Lari | Nyanduma | 2024-12-01 | 2025-06-01 |  | 1670000 | Ongoing
180 | Construction of burning chamber at Kihara hospital | Kiambaa | Kihara | 2023-07-01 | 2024-12-01 |  | 2,773,430 .00 | Ongoing
181 | Renovation and refurbishment at Gathanga hospital | Kiambaa | Mucatha | 2024-07-01 | 2024-12-01 |  | 10000000 | Complete
182 | Renovation and refurbishment of Kahuho dispensary | Kabete | Muguga | 2024-07-01 | 2025-06-01 |  | 10000000 | Complete
183 | Renovation and refurbishment of Kihara level 4 hospital-phase II | Kiambaa | Kihara | 2025-03-01 | 2027-03-01 |  | 55640460 | Ongoing
184 | Renovation and refurbishment of Ngoliba health centre-Phase II | Thika | Ngoliba | 2025-03-01 | 2026-03-01 |  | 24000000 | Ongoing
185 | Renovation and refurbishment of Kinale dispensary | Lari | Kinale | 2024-07-01 | 2024-12-01 |  | 6807120 | Complete
ADMINISTRATION AND PUBLIC SERVICE
FY 2014/15
1 | LAN Installation | Gatundu North | Kamwangi | 2014-04-01 | 2014-06-01 | 2014-06-01 | 3883801 | Complete
2 | Conversion of existing works from Municipal council offices to Executive County offices at Kiambu HQ | Kiambu | Kiambu township | 2014-11-01 | 2014-06-01 | 2014-06-01 | 22196095 | Complete
3 | Prefabricated office structures erecting ward admin offices | Juja | Theta | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
4 | Prefabricated office structures erecting ward admin office | juja | Witeithie | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
5 | Prefabricated office structures erecting ward admin office | Githunguri | Ikinu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
| Prefabricated office structures erecting ward admin office | Lari | Nyanduma | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
7 | Prefabricated office structures erecting ward admin office | Lari | Kijabe | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
8 | Prefabricated office structures erecting ward admin office | kikuyu | Ndeiya | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
9 | Prefabricated office structures erecting ward admin office | Gatundu North | Githobokoni | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
10 | Prefabricated office structures erecting ward admin office | Gatundu North | Gituamba | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
11 | Prefabricated office structures erecting ward admin office | Limuru | Limuru central | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
12 | Prefabricated office structures erecting ward admin office | Limuru | Nyathuna | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
13 | Prefabricated office structures erecting ward admin office | Kabete | Wangige | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
14 | Prefabricated Office Structures Erecting ward admin office | Thika | Ndarugu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1534105 | Complete
FY 2015/16
15 | Proposed construction of Juja Sub County Offices | Juja | Juja | 2015-06-01 | 2024-02-01 | 2024-02-01 | 56767898.85 | Complete
16 | Proposed rehabilitation and refurbishment Works at County Community Hall, Kiambu | Kiambu | Kiambu township | 2015-07-01 | 2016-06-01 | 2016-06-01 | 14396339 | Complete
17 | Construction of entrance gates at Kiambu HQ | Kiambu | Kiambu township | 2015-05-01 | 2016-06-01 | 2016-06-01 | 3200000 | Complete
18 | Juja sub county offices-to pay works completed from previous years | Juja | Juja | 2015-06-01 | 2016-06-01 | 2016-06-01 | 49459500 | Complete
19 | Kiambu Wall plastering and stone dressing cabro works for parking and extension road | Kiambu | Kiambu township | 2015-05-01 | 2016-06-01 | 2016-06-01 | 3345000 | Complete
20 | Supply, Installation and commissioning of Security lighting, electric fencing and razor wire at Kiambu HQ | Kiambu | Kiambu township | 2015-05-01 | 2016-06-01 | 2016-06-01 | 3990000 | Complete
21 | Supply of 60 KVA Generators HQ | Kiambu | Kiambu township | 2016-04-01 | 2016-06-01 | 2016-06-01 | 1930000 | Complete
22 | Supply of 3 phase Voltage Stabilizer HQ | Kiambu | Kiambu township | Oct. 2016 | Nov. 2016 | Nov. 2016 | 1711580 | Complete
23 | Supply of 3 phase Voltage Stabilizer HQ | Kiambu | Kiambu township | July, 2016 | Aug, 2016 | Aug, 2016 | 1327040 | Complete
24 | Construction of entrance/exit gates at HQ Kiambu | Kiambu | Kiambu township | 9th May, 2015 | 19th Feb, 2016 | 19th Feb, 2016 | 3,200,000,00 | Complete
25 | Improvement of boundary wall at county HQ | Kiambu | Kiambu township | 15th May, 2015 | 8th Feb, 2016 | 8th Feb, 2016 | 3345000 | Complete
FY 2017/18
26 | Proposed Development of Kiambu County Investor Enabling Centre | Kiambu | Kiambu township | 2017-01-01 | 2018-08-01 | 2018-08-01 | 6926599.6 | Complete
27 | Proposed conversion of former Kiambu sub county revenue offices to county executive offices | Kiambu | Kiambu township | 2017-11-01 | 2018-08-01 | 2018-08-01 | 13567668 | Complete
28 | Supply & delivery of changeover, cables & generator commissioning at Kiambu HQ | Kiambu | Kiambu township | April, 2017 | 2017-06-01 | 2017-06-01 | 1257743.2 | Complete
29 | Conversion of former Kiambu sub county revenue offices to county executive offices HQ | Kiambu | Kiambu township | 2017-07-01 | 2018-06-01 | 2018-06-01 | 13567668 | Complete
30 | Construction of Generator room for Governor's office Kiambu | Kiambu | Kiambu township | 2017-02-01 | 2017-06-01 | 2017-06-01 | 1384259 | Complete
31 | Renovation to County Headquarters Governors wing | Kiambu | Kiambu township | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3670084 | Complete
32 | Renovations to County HQs office including Deputy Governor's wing | kiambu | Kiambu township | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3756241 | complete
FY 2018/19
33 | Proposed refurbishment of Kahawa Wendani administration | Ruiru | Kahawa Wendani | 2018-01-01 | 2018-05-01 | 2018-05-01 | 1914660 | Completed
34 | Proposed Bio-Digester at Investor Enabling Centre Kiambu | Kiambu | Kiambu township | 2018-06-01 | August, 2018 | August, 2018 | 1497742 | Complete
35 | Construction of Kiambu sub county | Kiambu | Kiambu township | 2019-01-01 | June, 2020 | June, 2020 | 15356330 | Complete.
FY 2023/2024
36 | Proposed Rehabilitation of Gatundu North Sub-County Offices | Gatundu north | Kamwangi | 4th Nov. 2023 | 2024-06-01 | 2024-06-01 | 4782385 | Complete
37 | Proposed Sub-County Offices in Lari Sub-County | Lari Sub County | Lari | 2023-06-01 | 2024-06-01 | 2024-06-01 | 12399790 | Complete
38 | Proposed Renovation Works at Githunguri Sub-County Offices | Githunguri | Githunguri | 8th May 2023 | 2024-06-01 | 2024-06-01 | 3662240 | Complete
39 | Renovation of Kabete Sub County offices | Kabete | Kabete | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2999528 | Complete
40 | Construction of executive kitchen and boardroom at Kiambu HQ | Kiambu | Kiambu township | 2023-07-01 | 2024-06-01 | 2024-06-01 | 4594719 | Complete
41 | Renovation at Kiambu County Headquarters | Kiambu | Kiambu township | 22nd April 2024 | 22nd Oct. 2024 | Oct. 2024 | 8988558 | Complete
42 | Kiambu carpark extension | Kiambu | Kiambu township | 2023-07-01 | 2024-06-01 | 2024-06-01 | 5000000 | Complete
2024/2025
43 | Refurbishment of existing county offices at Thika sub county | Thika | Thika township | 19th February 2024 | 19th Aug. 2024 | 2024-08-01 | 4706100 | Complete
LAND, HOUSING, PHYSICAL PLANNING, URBAN DEVELOPMENT AND ADMINISTRATION
FY 2015/2016
1 | Conversion, Renovations & Refurbishment of former Red Nova Hotel | Kiambu | Township | 2015-06-01 | 2016-06-01 | 2016-06-01 | 23609320 | Completed
FY 2017/2018
2 | Proposed construction of a perimeter fence, gatehouse and landscaping | Kiambu | Township | 2017-03-01 | 2018-09-01 | 2018-09-01 | 19759470 | Completed
3 | Proposed refurbishment works at Thika Depot flats on Block A 9/108 | Thika | Township | 2017-10-01 | 2018-06-01 |  | 21740702 | Stalled
4 | Proposed refurbishment works at Thika Depot flats on Block B 9/109 | Thika | Township | 2017-10-01 | 2018-06-01 |  | 25725920 | Stalled
FY 2018/2019
5 | Proposed construction of Muiltistorey office block at Red Nova | Kiambu | Township | 2018-07-01 | 2021-06-01 | 2021 June | 80999910 | Completed
FY 2020/2021
6 | Proposed construction of Kiambu County Residential Buildings in kikuyu Municipality | Kikuyu | Township | 2021-06-01 | 2022-07-01 | 2022-07-01 | 11325085 | Completed
7 | Proposed Internal and External renovations of offices at Red Nova | Kiambu | Township | 2021-06-01 | 2022-06-01 | 2022-06-01 | 4588159 | Completed
FY 2021/2022
8 | Upgrading of Equity –Rwaka Slaughter Road to Bituminous Standards and Upgrading of Muchatha Access Road (400m) to Cabro Standards | Kiambaa | Muchatha | 2021-07-01 | 2022-06-01 | 2022-06-01 | 68669596.81 | Completed
9 | Upgrading of Ruiru Town Parking Lots and NMT to Paving Blocks Standards & Improved Drainage | Ruiru | Biashara | 2021-07-01 | 2023-06-01 | 2023-06-01 | 50307083.63 | Completed
FY 2022/2023
10 | Upgrading of Gitothua -Mama Shop-Bypass Road and 300 Meter in Gatongora to Bituminous Standards | Ruiru | Gitothua | 2022-07-01 | 2023-06-01 | 2023-06-01 | 47044829.98 | Completed
11 | Upgrading Of Kahawa Wendani Maguna- Kiu River Road To Bitumen Standards | Ruiru | Kahawa-Wendani | 2022-07-01 | 2023-06-01 | 2023-06-01 | 46136510.82 | Completed
12 | Upgrading of Nyambari Access Road to Bituminous standards and Construction of Kimende Market Shed | Limuru | Bibirioni and Kimende | 2022-07-01 | 2023-06-01 | 2023-06-01 | 47782131 | Completed
13 | Upgrading of Ondiri Road 0.9Km to Bituminous Standards(phase I) | Kikuyu | Kikuyu | 2022-07-01 | 2023-06-01 | 2023-06-01 | 50534962.1 | Completed
14 | Upgrading of Kidfarmco Road 1.15Km to Bituminous Standards and street lighting | Kikuyu | Kikuyu | 2022-07-01 | 2023-06-01 | 2023-06-01 | 78733234.94 | Completed
15 | Upgrading of Mwimuto Access Road, Kiharu Drive, Wambaa outfall drain, Kikuyu NMT, Jeevanjee Ablution Block and Lusiggetti Market sheds | Kikuyu, Kabete | Kikuyu, Nachu, Kabete | 2022-07-01 | 2023-06-01 | 2023-06-01 | 99951506.49 | Completed
16 | Establishment and Construction of Light Industrial Garage and Posta Indian Bazaar Road (Phase3) | Kiambu | Township | 2022-07-01 | 2023-06-01 | 2023-06-01 | 31390926.11 | Completed
17 | Upgrading of Gwa- Kairu Road (1 Km) to Bituminous Standards | Thika | Juja | 2022-07-01 | 2023-06-01 | 2023-06-01 | 47214738.56 | Completed
18 | Proposed Construction of JKUAT Gate A –Uchumi Junction in Juja to Bitumen Standards | Thika | Juja | 2022-07-01 | 2023-06-01 | 2023-06-01 | 35000000 | Completed
FY 2024/2025
19 | Transaction consultancy and advisory services for Affordable Housing Program (AHP) | All Municipalities | All wards | 2024-07-01 | 2025-06-01 |  | 8700000 | Ongoing
ROADS, TRANSPORT, PUBLIC WORKS AND UTILITIES
FY 2013/2014
1 | Proposed construction of Kinenii-Karatina footbridge | Lari | Nyanduma | 2013-06-01 | 2013-09-01 | 2013-08-01 | 4998950 | Completed
2 | Proposed construction of footbridge at Gathiruini- Kamuchege | Githunguri | Kamburu | 2013-05-01 | 2013-09-01 | 2013-08-01 | 5189424 | Completed
3 | Proposed construction of footbridge at Ngegu-Indian bazaar | Kiambu | Kiambu Township | 2013 | 2013-09-01 | 2013-07-01 | 4444990.5 | Completed
FY 2016/2017
5 | Proposed Fire Station at Kiambu | Kiambu | Kiambu Township | 2016-07-01 | 2016-12-01 | 2017-11-01 | 14394180 | Completed
FY 2018/2019
6 | Proposed Multi-Purpose Block for the Kiambu Sub-County Firestation | Kiambu | Kiambu township | 2018-08-01 | 2018-12-01 | 2018-12-01 | $211,306.24 | Completed
7 | Proposed masonry perimeter fence for Thika Sub County Fire Department | Thika | Thika Township | 2018-06-01 | 2018-07-01 | 2018-07-01 | 3997580 | Completed
8 | Proposed Guard House and Main Gate at Thika Fire station. | Thika | Thika Township | 2018-08-01 | 2018-08-01 | 2018-08-01 | 810000 | Completed
9 | Proposed masonry perimeter fence for Thika Sub County Fire Department | Thika | Thika Township | 2018-06-01 | 2018-07-01 | 2018-07-01 | 3997580 | Completed
FY 2019/2020
10 | Proposed Construction and Rehabilitation of Athena Footbridge (40m Span) in Kiandutu | Thika | Thika Township | 2019-02-01 | 2019-06-01 | 2019-08-01 | 2412500 | Completed
11 | Proposed Construction of A 2no. Storey Fire Station at Karuri | Kiambaa | Karuri | 2019-03-01 | 2019-06-01 | 2020-12-01 | 63430800 | Completed
12 | Proposed construction of Decoma-Gwa Kigwi Footbridge- 24m Span | Juja | Kalimoni | 2020-01-01 | 2020-04-01 | 2020-01-01 | 4693890 | Completed
FY 2020/2021
13 | Proposed construction of Kairi Gatono-Nyamathumbi Kamwangi Footbridge (24m Span) | Gatundu North | Chania | 2020-01-01 | 2020-06-01 | 2021-08-01 | 3523720 | Completed
14 | Proposed construction of Loreto and Riara Footbridges (15m Span Each) | Kiambu | Ndumberi | 2020-01-01 | 2020-06-01 | 2020-06-01 | 4072730 | Completed
15 | Proposed construction of Footbridge at Kairi-Nyamathumbi (Mang'u) | Gatundu North | Chania | 2020-01-01 | 2020-06-01 | 2020-10-01 | 2491070 | Completed
FY 2023/2024
16 | Proposed construction of Kiambururu – Gitombo (Kianue) Footbridge 15m span | Githunguri | Komothai | 2023-06-01 | 2023-09-01 | 2023-08-01 | 2369021.6 | Completed
17 | Proposed construction of Kianda-Kinene-Kibiru Footbridge (18m span) | Gatundu South | Ndarugu | 2023-06-01 | 2023-09-01 | 2023-08-01 | 3764849.6 | Completed
18 | Proposed construction of Lioki - Giathieko Footbridge (10m span) | Githunguri | Ngewa | 2023-06-01 | 2023-09-01 | 2023-08-01 | 1658985.6 | Completed
19 | Proposed construction of Gakoe-Muchakai footbridge (15m span) | Gatundu North | Githobokoni | 2023-06-01 | 2023-09-01 | - | 2509868 | Ongoing
20 | Proposed construction of Footbridge Works at Munyu-Komo (Githima) 24m Span | Thika | Gatuanyaga | 2023-06-01 | 2023-09-01 | 2023-08-01 | 4862116 | Completed
21 | Maintenance and Rehabilitation of County Access Roads | All Sub-Counties | All Wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 511506295 | Completed
22 | Construction of Makongeni Bus Park | Thika | Kamenu | 2023-06-01 | 2023-11-01 | 2024-01-01 | 30000000 | Completed
23 | Solar street lighting installation | All Sub-Counties | All wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 338000000 | Completed
24 | Maintenance works of streetlights and flood masts. | All Sub-Counties | All Wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 95000000 | Completed
25 | Supply, installation and commission of grind connected streetlights. | Kiambaa and Kabete | Nyathuna and Karuri | 2023-07-01 | 2023-12-01 | 2024-06-01 | 17000000 | Completed
26 | Proposed Footbridge Works at Githima Muguti (15m Span) | Githunguri | Komothai | 2023-08-01 | 2024-01-01 | 2024-12-01 | 2550000 | Completed
FY 2024/2025
27 | Supply and delivery of culverts. | All Sub-Counties | All Wards | July 2024 | 2025-06-01 | - | 116000000 | Ongoing
28 | Maintenance and Rehabilitation of County Access Roads | All Sub-Counties | All Wards | July 2024 | 2025-06-01 | 2025-06-01 | 635920000 | Completed
29 | Completion of Darasha Motorable Bridge | Juja | Theta | May 2017 | 2025-06-01 | - | 16208453 | Ongoing
30 | Completion of Mugutha Motorable Bridge | Juja | Theta | May 2017 | 2025-06-01 | - | 14888240 | Ongoing
31 | Completion of Riuriro Motorable Bridge | Juja | Theta | May 2017 | 2025-06-01 | - | 23200373 | Ongoing
32 | Construction of Bosnia Bridge | Ruiru | Kahawa Wendani/Kiu | 2023-07-01 | 2024-12-01 | 2024-12-01 | 15000000 | Completed
33 | Construction of Mariguiti-Gituamba bridge | Gatundu South | Kiganjo | 2024-07-01 | 2024-12-01 | - | 6516358 | Ongoing
34 | Construction of Miumia bridge | Githunguri | Githiga | 2024-08-01 | 2025-01-01 | - | 10927477.7 | Ongoing
35 | Hiring of specialized plant | Ruiru | Gatongora | 2024-07-01 | 2025-06-01 | 2025-06-01 | 50000000 | Completed
36 | Construction of Karuri bus park | Kiambaa | Karuri | 2023-07-01 | 2023-12-01 | 2024-06-01 | 8764971.6 | Completed
37 | Upgrading of Banana bus park road to paving block | Kiambaa | Karuri | 2023-07-01 | 2023-12-01 | 2024-06-01 | 4580086.6 | Completed
38 | Construction of Kiambu Bus Park | Kiambu | Township | 2023-06-01 | 2023-11-01 | 2024-04-01 | 17263111 | Completed
39 | Construction of Kikuyu bus park | Kikuyu | Kikuyu Township | 2023-06-01 | 2023-11-01 | 2024-04-01 | 17712016.8 | Completed
40 | Construction of 17 modern Kiosks in Kikuyu bus park | Kikuyu | Kikuyu Township | 2023-06-01 | 2023-11-01 | 2024-04-01 | 3700000 | Completed
41 | Construction of Kwamaiko bus park | Githunguri | Ngewa | 2023-07-01 | 2023-12-01 | 2024-06-01 | 10523520 | Completed
42 | Construction of Kwambira bus park | Limuru | Limuru Central | 2024-05-01 | 2024-10-01 | 2024-11-01 | 43028468 | Completed
43 | Construction of Githiga bus park | Githunguri | Githiga | 2024-05-01 | 2024-10-01 | 2024-11-01 | 7768694 | Completed
44 | Rehabilitation of Thika Main bus park | Thika | Thika Township | 2024-07-01 | 2024-12-01 | - | 15000000 | Ongoing
45 | Fabrication and installation of steel shed and steel modern kiosks in Makongeni bus park | Thika | Kamenu | 2024-03-01 | 2024-07-01 | 2024-07-01 | 4968136 | Completed
46 | Construction of modern Kiosks at Kiambu bus park | Kiambu | Kiambu Township | 2024-07-01 | 2024-12-01 | - | 20000000 | Ongoing
47 | Additional works at Kiambu bus park | Kiambu | Kiambu Township | 2024-07-01 | 2024-12-01 | - | 5000000 | Ongoing
48 | Installation of 4000 solar street lights | All Sub-Counties | All wards | 2024-07-01 | 2025-06-01 | 2025-06-01 | 240000000 | Completed
49 | Maintenance of street lights and flood masts | All Sub-Counties | All wards | 2024-07-01 | 2025-06-01 | - | 24000000
50 | Procurement of 3700 solar street lights and 32 solar floodlights | All Sub-Counties | All wards | 2024-07-01 | 2025-06-01 | 2025-06-01 | 360000000 | Completed
51 | Construction of Limuru fire station | Limuru | Limuru Central | 2017-07-01 | 2017-12-01 | - | 34036113 | Ongoing
52 | Construction of Githunguri fire station | Githunguri | Githunguri | 2017-07-01 | 2017-12-01 | - | 37913625 | Ongoing
53 | Purchase of Extrication equipment | Thika Sub-County | Thika Township | 2023-07-01 | 2023-12-01 | 2024-06-01 | 3950000 | Completed
54 | Purchase of Water rescue equipment | Thika, Ruiru, Kiambu and Kiambaa Sub-Counties | Biashara, ThikaTownship, Kiambu Township and Karuri | 2023-07-01 | 2023-12-01 | 2024-06-01 | 3860000 | Completed
55 | Purchase of Rope rescue equipment | Limuru, Kikuyu, Kiambaa, Kiambu, Ruiru, Githunguri and Thika Sub-Counties | Limuru Central, Kikuyu Township, Karuri, Kiambu Township, Biashara, Githunguri and Thika Township | 2024-07-01 | 2024-12-01 | 2025-06-01 | 11000000 | Completed
STALLED PROJECTS
56 | Construction of Gatitu Junction and other roads in Thika | Thika | Thika Township | 2015-07-01 | 2022-06-01 | 2022-06-01 | 221005870.3 | Project stalled
57 | Construction of Thogoto-Ndaire Road | Kikuyu | Kikuyu | 2017-03-01 | 2018-09-01 | 2018-09-01 | 181452509.9 | Project stalled
58 | Upgrading of Kimende town roads | Lari | Kijabe | 2017-03-01 | 2018-09-01 | 2018-09-01 | 145000000 | Project stalled
YOUTH AFFAIRS, SPORTS AND COMMUNICATION
FY 2014/2015
1 | Proposed rehabilitation and upgrading of Kaburu sports ground | Lari | Nyanduma | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
2 | Proposed rehabilitation and upgrading of Githunguri sports ground | Githunguri | Githunguri township | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
3 | Proposed rehabilitation and upgrading of Kamangu primary school sports ground | Kikuyu | Nachu | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
4 | Proposed rehabilitation and upgrading of Thigio sports ground | Limuru | Ndeiya | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
5 | Proposed rehabilitation and upgrading of Tharuni primary school sports ground | Limuru | Limuru central | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
6 | Proposed rehabilitation and upgrading of Kiawaroga primary sports ground | Limuru | Limuru East | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
7 | Proposed rehabilitation and upgrading of Karia sports field | Githunguri | Ikinu | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
8 | Proposed rehabilitation and upgrading of Kinoo primary school sports ground | Kikuyu | Kinoo | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
9 | Proposed rehabilitation and upgrading of Kawaida sports ground | Kiambaa | Cianda | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
10 | Proposed rehabilitation and upgrading of Gachie sports ground | Kiambaa | Kihara | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
11 | Proposed rehabilitation and upgrading of Uthiru primary school ground | Kabete | Uthiru | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
12 | Proposed rehabilitation and upgrading of Ndenderu primary school sports ground | Kiambaa | Ndenderu | 2015-01-01 | 2016 | 2016 | 1000000 | Completed
13 | Proposed rehabilitation and upgrading of Nyanduma youth polytechnic sports ground | Lari | Nyanduma | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
14 | Proposed rehabilitation and upgrading of Muchatha sports ground | Kiambaa | Muchatha | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
15 | Proposed rehabilitation and upgrading of Kiambururu primary school sports ground | Githunguri | Ngewa | 2015-01-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
16 | Proposed rehabilitation and upgrading of Muguga sports ground | Kabete | Muguga | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
17 | Proposed rehabilitation and upgrading of Ndumberi sports ground | Kiambu | Ndumberi | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
FY 2015/2016
18 | Proposed rehabilitation for Garissa Road primary school ground | Thika | Ngoliba | July, 2015 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
19 | Proposed rehabilitation for Nyamathumbi primary school ground | Gatundu North | Mang'u | 2016-01-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
20 | Proposed rehabilitation for Ngoliba primary school ground | Thika | Ngoliba | July, 2015 | 2015-11-01 | 2015-11-01 | 1000000 | Completed
21 | Proposed rehabilitation for Wendani Ward ground | Ruiru | Kahawa Wendani | July,2015 | 2015-11-01 | 2015-11-01 | 1000000 | Completed
22 | Proposed rehabilitation for Kiriko Primary School grounds | Gatundu North | Gituamba | July,2015 | 2015-11-01 | 2015-11-01 | 1000000 | Completed
23 | Proposed rehabilitation and upgrading of Kiambu primary school sports ground | Kiambu | Kiambu township | Jan,2015 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
24 | Proposed rehabilitation and upgrading of Gathangari sports ground | Kiambaa | Muchatha | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
25 | Proposed rehabilitation and upgrading of Karuri Secondary school sports ground | Kiambaa | Karuri | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
26 | Proposed rehabilitation and upgrading of Kihara sports ground | Kiambaa | Kihara | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
27 | Proposed rehabilitation and upgrading of Kibichiko sports ground | Kabete | Kabete | 2015-01-01 | 2015-10-01 | 2015-10-01 | 1000000 | Completed
28 | Proposed rehabilitation and upgrading of Ruiru stadium football Grounds | Ruiru | Biashara | 2015-01-01 | 2017-09-01 | 2017-09-01 | 1000000 | Completed
29 | Proposed rehabilitation and upgrading of Kagwe stadium football Grounds | Lari | Nyanduma | 2015-01-01 | 2026-06-15 | 2026-06-15 | 1000000 | Completed
30 | Proposed rehabilitation and upgrading of Gikambura stadium football Grounds | Kikuyu | Karai | 2015-01-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
31 | Proposed Rehabilitation and upgrading of Garrissa Road primary school ground | Thika | Township | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
32 | Proposed Rehabilitation and upgrading Nyamathumbi of Primary school ground | Gatundu North | Mang'u | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
33 | Proposed Rehabilitation and upgrading of Ngoliba Primary School sports ground | Thika | Ngoliba | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
34 | Proposed Rehabilitation and Upgrading of Kiriko Primary School Grounds | Gatundu North | Gituamba | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
35 | Proposed Rehabilitation and Upgrading of Kiganjo Sports ground | Gatundu South | Kiganjo | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
36 | Proposed Rehabilitation and Upgrading of Toll area Sports ground | Juja | Murera | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
37 | Proposed Rehabilitation and Upgrading of Theta Secondary school sports ground | Juja | Theta | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
38 | Proposed rehabilitation and upgrading of St. Patrick Primary school ground | Thika | Hospital | 2015-07-01 | 2016-05-01 | 2016-05-01 | 900000 | Completed
39 | Proposed Rehabilitation and upgrading of Gachege Sports ground | Gatundu North | Githobokoni | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
40 | Proposed Rehabilitation and upgrading of Gachororo Primary school sports ground | Juja | Theta | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
41 | Proposed Rehabilitation of Thika stadium | Thika | Thika township | 2015-07-01 | 2016-05-01 | 2016-05-01 | 14529230 | Completed
42 | Proposed rehabilitation and upgrade of Kiganjo sports ground | Thika | Hospital | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
43 | Proposed rehabilitation and upgrade of Mwihoko secondary school sports ground | Ruiru | Mwihoko | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
44 | Proposed rehabilitation and upgrade of Gathiru primary school ground | Gatundu South | Ngenda | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
45 | Proposed rehabilitation and upgrading of Nembu sports ground | Gatundu South | Kiamwangi | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
46 | Ditto but rehabilitation and upgrading of BTL sports ground | Ruiru | Gitothua | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
47 | Proposed rehabilitation and upgrading at Karatu stadium | Gatundu South | Ndarugo | 2015-07-01 | 2016-05-01 | 2016-05-01 | 1000000 | Completed
48 | Proposed rehabilitation of Thika stadium | Thika | Thika Township | 2015-07-01 | 2016-09-01 | 2016-09-01 | 14529230 | Completed
49 | Proposed rehabilitation and upgrading of Muchatha sports ground | Kiambaa | Muchatha | 2015-01-01 | 2016 | 2016 | 1000000 | Completed
50 | Proposed rehabilitation and upgrading of Kamunyonge sports ground | Kiambu | Ting’ang’a | 2015-01-01 | 2016 | 2016 | 1000000 | Completed
FY 2024/2025
51 | Proposed Renovations and Alterations at Thika Stadium Phase I | Thika | Thika Township | 2024-07-01 | 2025-07-01 | 2025-07-01 | 31503143 | Completed
52 | Proposed Renovations and Alterations at Thika Stadium phase II | Thika | Thika Township | 2023 | 2025 | 2025 | 165669431 | Ongoing
53 | Proposed Renovations & Alterations at Thika stadium in Thika Sub-County (Phase 1) | Thika stadium | Thika Township | 2024-01-01 | 2025 | 2025 | 31253143 | Ongoing
54 | Proposed Upgrading of Kanjeru Stadium in Gitaru Ward, Kiambu County | Kabete | Gitaru | 2024-03-01 | 2025 | 2025 | 163875850 | Ongoing
55 | Proposed Construction of Thika Stadium Basketball Pitch, Stalls, Steel Bleachers, Swimming Pool, Changing Rooms &Borehole at Thika Stadium (Phase 2) | Thika | Thika Township | 2024-07-01 | 2025 | 2025 | 165699431 | Ongoing
56 | Proposed rehabilitation of Gachie grounds | Kiambaa | Kihara | 2024-07-01 | 2025 | 2025 | 3631558 | Complete
AGRICULTURE, LIVESTOCK AND COOPERATIVES
FY 2018/2019
1 | Proposed renovation works for veterinary offices in Thika | Thika | Township | 2018-08-01 | 2018-10-01 |  | 1241300 | Completed
FY 2020/2021
2 | Proposed Perimeter wall at Thika slaughter house | Thika | Hospital | 2020-03-01 | 2021 |  | 13455640 | Completed
3 | Kamwamba Irrigation Scheme | Gatundu North | Chania/Mang'u | 2020-01-01 | 2022-09-01 | 2022-09-01 | 89511073 | Completed
FY 2024/2025
4 | Proposed Renovations of Thika Main Slaughter House and Perimeter Fence Construction | Thika | Hospital | 2024-05-01 | 2024-11-01 |  | 16631390 | Ongoing
5 | Proposed Renovation Works to NAVCPP office Thika Office | Thika | Township | 2024-09-01 | 2024-10-01 |  | 2487230 | Completed
6 | Proposed Construction of a Perimeter Wall at Komothai Coffee Grower's Co-Operative Society Limited in Kiambu County | Githunguri | Komothai | 2024-11-01 | 2024-12-01 |  | 4979800 | Completed
WATER, ENVIRONMENT, NATURAL RESOURCES, ENERGY AND CLIMATE CHANGE
FY 2013-2014
1 | Ting’ang’a water project- Ting’ang’a Ward- Lay of 3.8 km water main pipeline(4&3)’’Ø pipeline, installation of distribution pipes and construction of elevated 100 m3 steel tank. | Kiambu | Ting’ang’a | 2013-07-01 | 2014-06-01 | 2014-06-01 | 4510892 | Completed
FY 2014-2015
2 | Gitiha water project/ Githiga Ward Trenching, pipe laying and backfilling of 2km long 6’’ Ø pipeline | Githunguri | Githiga | 2014-07-01 | 2015-06-01 | 2015-06-01 | 500000 | Completed
3 | Getango-Muguga water project Trenching pipe lying and backfilling of 2.4km long 6’’ Ø pipeline from Getango-Muguga water project and intake, pump house and electrification | Kabete | Muguga | 2014-07-01 | 2015-06-01 | 2015-06-01 | 250000 | Completed
4 | Kaimba river intake water project- Muguga/ Kabete Ward Trenching pipe laying and backfilling of 2.5km long 4’’ Ø pipeline from Kaimba river to Ruku Police Post | Kabete/Kikuyu | Muguga | 2014-07-01 | 2015-06-01 | 2015-06-01 | 700000 | Completed
5 | Juja Salama borehole Removal of burnt motor from the borehole and re-equipping with a new motor | Juja | Kalimoni | 2014-07-01 | 2015-06-01 | 2015-06-01 | 300000 | Completed
6 | Lussigetti community borehole- Nachu Rehabilitation of a borehole by equipping it | Kikuyu | Nachu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 400000 | Completed
7 | Mwiki bore hole Operationalizing of the borehole | Ruiru | Mwiki | 2014-07-01 | 2015-06-01 | 2015-06-01 | 520000 | Completed
8 | Ondiri Water Project Trenching, pipe laying and backfilling of 4.2km long 6’’ Ø pipeline | Kikuyu | Kikuyu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 8800000 | Completed
9 | Makwa – Chania water supply project - Supply of 110mm upvc 670 No.pipes | Gatundu North | Gituamba | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1500000 | Completed
10 | Gakoe-Githobokoni water supply project | Gatundu south | Githobokoni | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1500000 | Completed
11 | Muchakai- Gituamba water supply project | Gatundu North | Gituamba | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
12 | Kairi- Mary Hill Tank water supply project -pipe Extension to serve Ngoingwa/ Mangu- Investiment and Karibaribi areas | Thika/Gatundu North | Hospital/Chania | 2014-07-01 | 2015-06-01 | 2015-06-01 | 5000000 | Completed
13 | Kiuu Ward water supply project – 6” pipes | Ruiru | Kiuu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1500000 | Completed
14 | Mwihoko water supply project | Ruiru | Mwihoko | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
15 | Gitombo Borehole water supply project | Githunguri | komothai | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1600000 | Completed
16 | Kimunyu –Kenyatta water supply project | Gatundu South | Ngenda | 2014-07-01 | 2015-06-01 | 2015-06-01 | 20000000 | Completed
17 | Muchakari water supply project | Kiambu | Ndumberi | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
18 | Igegania Gakao A&B water supply project | Gatundu north | Mangu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1000000 | Completed
19 | Cura pipeline extension water supply project | Kabete | Gitaru | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1500000 | Completed
20 | Gikari/Gituamba water supply project | Gatundu north | Gituamba | 2014-07-01 | 2015-06-01 | 2015-06-01 | 200000 | Completed
21 | Kamunyaka water supply project | Gatundu north | Githobokoni | 2014-07-01 | 2015-06-01 | 2015-06-01 | 600000 | Completed
22 | Rwaka-Gacharage-Karuri,Muchatha-Wanguthu-Kimuga-Karure-Ndenderu water supply project | Kiambaa | Ndenderu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 7000000 | Completed
23 | Kimende –Kijabe*Upgrade* Mbariki-Karanya mwenji watersupply project | Lari | Kijabe | 2014-07-01 | 2015-06-01 | 2015-06-01 | 6000000 | Completed
24 | Procurement of 5 waste management trucks | County wide | County wide | 2014-07-01 | 2015-06-01 | 2015-06-01 | 45000000 | Completed
25 | Procurement of one D7 bulldozer | Thika | Kamenu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 22000000 | Completed
26 | Procurement of one backhoe | Thika | Kamenu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 8000000 | Completed
27 | Establishment of Kangoki pilot landfill | Thika | Kamenu | 2014-07-01 | 2015-06-01 | 2015-06-01 | 9000000 | Completed
28 | Procurement of pressurized washing machine, welding machine and accessories, projector and public address and genset | Thika | Thika Township | 2014-07-01 | 2015-06-01 | 2015-06-01 | 1200000 | Completed
29 | Procurement of 24 skips | County wide | County wide | 2014-07-01 | 2015-06-01 | 2015-06-01 | 5280000 | Completed
FY 2015/2016
30 | Construction of Kanunga weir | Kiambu | Cianda | 2015-07-01 | 2016-06-01 | 2016-06-01 | 371500 | Completed
31 | Laying of pipes in Kiamumbi | Kiambu | Kiambu | 2015-07-01 | 2016-06-01 | 2016-06-01 | 485740 | Completed
32 | Procurement of 225mm pipes -110No. and 160mm pipes -70No Mwiki –Githurai | Ruiru | Mwiki | 2015-07-01 | 2016-06-01 | 2016-06-01 | 1936000 | Completed
33 | Drilling of borehole at Mwihoko | Ruiru | Mwihoko | 2015-07-01 | 2016-06-01 | 2016-06-01 | 1995664 | Completed
34 | Drilling of borehole at Kanyariri | Kabete | Gitaru | 2015-07-01 | 2016-06-01 | 2016-06-01 | 1995664 | Completed
35 | Equipping of the borehole in Thami | Kikuyu | Kikuyu | 2015-07-01 | 2016-06-01 | 2016-06-01 | 1280000 | Completed
36 | Laying of pipes ,supply of fittings and construction of chambers at Cura | Kabete | Gitaru | 2015-07-01 | 2016-06-01 | 2016-06-01 | 2018166 | Completed
37 | Procurement of 2 waste management trucks | County wide | County wide | 2015-07-01 | 2016-06-01 | 2016-06-01 | 19000000 | Completed
38 | Procurement of 10 skips | County wide | County wide | 2015-07-01 | 2016-06-01 | 2016-06-01 | 2200000 | Completed
FY 2016/2017
39 | Procurement of 2 waste management trucks | County wide | County wide | 2016-07-01 | 2017-06-01 | 2017-06-01 | 19000000 | Completed
40 | Procurement of 2 exhausters | County wide | County wide | 2016-07-01 | 2017-06-01 | 2017-06-01 | 24000000 | Completed
41 | Procurement of 10 skips | County wide | County wide | 2016-07-01 | 2017-06-01 | 2017-06-01 | 2200000 | Completed
FY 2017/2018
42 | Kiambu Water Company office rehabilitation | Kiambu | Kiambu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3700000 | Completed
43 | Rehabilitation of ground masonary nyathuna water project | Kabete | Nyathuna | 2017-07-01 | 2018-06-01 | 2018-06-01 | 1300000 | Completed
44 | Rehabilitation of Thika Town garage toilet | Thika | Thika | 2017-07-01 | 2018-06-01 | 2018-06-01 | 1060000 | Completed
45 | Rehabilitation of Makongeni toilet | Thika | Kamenu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2650000 | Completed
46 | Rehabilitation of Madaraka toilet | Thika | Thika | 2017-07-01 | 2018-06-01 | 2018-06-01 | 1890000 | Completed
47 | Rehabilitation of Ndenderu toilet | Kiambaa | Ndenderu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 175000 | Completed
48 | Ruaka public sanitation water connection water supply project | Kiambaa | Ndenderu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 1990000 | Completed
49 | Makongeni market sewer augmentation | Thika | Kamenu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 972000 | Completed
50 | Rehabilitation of Kiambu bus park toilet | Kiambu | Kiambu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3990000 | Completed
51 | Rehabilitation of Governors office toilet | Kiambu | Kiambu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3990000 | Completed
52 | Construction of Rukuma toilet | Lari | Lari | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2500000 | Completed
53 | Construction of Lussigetti public sanitation | Kikuyu | Nachu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2600000 | Completed
54 | Construction of Kwamaiko public sanitation | Githunguri | Ngewa | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2600000 | Completed
55 | Drilling of borehole at Ondiri swamp. | Kikuyu | Kikuyu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2950000 | Completed
56 | Construction of Kiuu ACK Borehole elevated Tank | Ruiru | Kiuu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3930000 | Completed
57 | Construction of Kimbo AP borehole elevated tank | Juja | Theta | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3950000 | Completed
58 | Drilling and equipping of Boreholes in Karuri at Karuri and Kiriaini | Kiambaa | Karuri | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3990000 | Completed
59 | Drilling of Ngabaini borehole | Kiambu | Riabai | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3580000 | Completed
60 | Drilling of Cianda borehole | Kiambaa | Cianda | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3210000 | Completed
61 | Drilling of Kiawaiguru borehole | Githunguri | Ikinu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3390000 | Completed
62 | Drilling of Mwamuto borehole | Kiambaa | Kihara | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3310000 | Completed
63 | Drilling of Thogoto borehole | Kikuyu | Kikuyu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3530000 | Completed
64 | Drilling of of 250Metres Nguirubi borehole | Limuru | Ndeiya | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2460000 | Completed
65 | Drilling of Kamangu borehole | Kikuyu | Nachu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3750000 | Completed
66 | Drilling of Kwa Mutiso borehole | Kiambu | Kiambu | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3460000 | Completed
67 | Drilling of Mutati borehole | Gatundu South | Kiamwangi | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3150000 | Completed
68 | Drilling of Kaspat borehole | Kiambaa | Cianda | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2460000 | Completed
69 | Drilling of Kabunge borehole | Kiambaa | Karuri | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2460000 | Completed
70 | Drilling of Ruiru hospital borehole | Ruiru | Biashara | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3260000 | Completed
71 | Drilling of Gatongora (Kwihota) b/h | Ruiru | Gatongora | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2950000 | Completed
72 | Drilling of Gitithia borehole | Lari | Lari kirenga | 2017-07-01 | 2018-06-01 | 2018-06-01 | 2430000 | Completed
73 | Drilling of a borehole at the Escarpment | Lari | Lari kirenga | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3300000 | Completed
74 | Drilling of a borehole and tank rehabilitation Igegania | Gatundu North | Chania | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3810000 | Completed
75 | Drilling of Kaimba bore hole | Kiambaa | Kihara | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3210000 | Completed
76 | Drilling of Ndumberi borehole | Kiambu | Ndumberi | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3300000 | Completed
77 | Drilling of Kerwa/Nduma bore hole | Kikuyu | Sigona | 2017-07-01 | 2018-06-01 | 2018-06-01 | 3140000 | Completed
FY 2018-2019
78 | Excavation and installation of pipes in Kijabe ward in Lari sub-county | Lari | Kijabe | 2018-07-01 | 2019-06-01 | 2019-06-01 | 1828073 | Completed
79 | Supply and installation of pipes in Gitithia borehole pipe network | Lari | Lari Kirenga | 2018-07-01 | 2019-06-01 | 2019-06-01 | 3004459 | Completed
80 | Construction of septic tanks in Kamangu, Thogoto and Rukuma | Kikuyu/lari | Nachu/Kijabe | 2018-07-01 | 2019-06-01 | 2019-06-01 | 2330070 | Completed
81 | Construction of bio-digester in Mutarakwa and Ndumberi | Kiambu | Ndumberi | 2018-07-01 | 2019-06-01 | 2019-06-01 | 2724249 | Completed
82 | Construction of 108M3 elevated steel in Ngecha community borehole | Limuru | Ngecha | 2018-07-01 | 2019-06-01 | 2019-06-01 | 3982682 | Completed
83 | Construction of control panel cum water kiosk at Kiawaiguru borehole | Githunguri | Ikinu | 2018-07-01 | 2019-06-01 | 2019-06-01 | 644705 | Completed
84 | Construction of panel house cum water kiosk at Uthiru primary school borehole | Kabete | Uthiru | 2018-07-01 | 2019-06-01 | 2019-06-01 | 654550 | Completed
85 | Construction of small public facility Kimende cemetery | Lari | Kijabe | 2018-07-01 | 2019-06-01 | 2019-06-01 | 1107995 | Completed
86 | Construction of small public facility of Kambaa cemetery | Githunguri | Githiga | 2018-07-01 | 2019-06-01 | 2019-06-01 | 1107995 | Completed
87 | Construction of a large toilet facility in Ruiru town. | Ruiru | Biashara | 2018-07-01 | 2019-06-01 | 2019-06-01 | 3690425 | Completed
88 | Constructions of public facility at Ngoliba open air market. | Thika | Ngoliba | 2018-07-01 | 2019-06-01 | 2019-06-01 | 2686335 | Completed
89 | Rehabilitation of Wendani and Ruiru public facility | Ruiru | Wendani | 2018-07-01 | 2019-06-01 | 2019-06-01 | 3880310 | Completed
FY 2019/2020
90 | Drilling of Kiu borehole | Ruiru | Kiuu | 2019-07-01 | 2020-06-01 | 2020-06-01 | 2136650 | Completed
91 | Drilling of Riu borehole 3 in Kikuyu region | Kikuyu | Karai | 2019-07-01 | 2020-06-01 | 2020-06-01 | 3018983 | Completed
92 | Drilling services for twin borehole in Kikuyu | Kikuyu | Kikuyu | 2019-07-01 | 2020-06-01 | 2020-06-01 | 1917399 | Completed
93 | Equipping services for Guirubi borehole In Ndeiya Ward | Limuru | Ndeiya | 2019-07-01 | 2020-06-01 | 2020-06-01 | 2237393 | Completed
94 | Ngurubi pipeline, Tank rehabilitation & Fencing | Limuru | Ndeiya | 2019-07-01 | 2020-06-01 | 2020-06-01 | 3874792 | Completed
95 | Solarization of Ngurubi borehole | Limuru | Ndeiya | 2019-07-01 | 2020-06-01 | 2020-06-01 | 1951335 | Completed
96 | Suply of Tigoni-Gachororo 10km 4'' water HDPE pipes | Kiambaa | Karuri | 2019-07-01 | 2020-06-01 | 2020-06-01 | 19916460 | Completed
FY 2020/2021
97 | Procuring, Supplying and Delivering of a 11km 6inch pipeline from Ondire to Kamangu primary transmitting 90m3/hr from Twin Borehole site | Kikuyu | Nachu | 2020-07-01 | 2021-06-01 | 2021-06-01 | 25000000 | Completed
98 | Supply and delivery of HDPE pipes and fittings to Kikuyu water and sanitation company for Rui-Karai water distribution network | Kikuyu | Kikuyu | 2020-07-01 | 2021-06-01 | 2021-06-01 | 5500000 | Completed
99 | Drilling of a borehole at Wangige level 4 hospital | Kabete | Kabete | 2020-07-01 | 2021-06-01 | 2021-06-01 | 3745692 | Completed
100 | Constructing a panel house cum water kiosk at Cianda High school | Kiambaa | Cianda | 2020-07-01 | 2021-06-01 | 2021-06-01 | 644705 | Completed
101 | Operationalization of Ha-gitonga borehole will involve,3 phase installation and fencing of the site | Lari | Lari/Kirenga | 2020-07-01 | 2021-06-01 | 2021-06-01 | 4000000 | Completed
102 | Githunguri Ikinu water distribution network HDPE pipes and fittings to Githunguri water and sewerage company for Githunguri Ikinu water distribution network line | Githunguri | ikinu | 2020-07-01 | 2021-06-01 | 2021-06-01 | 10000000 | Completed
103 | Kabunge Borehole operationalization will involve, construction of pump house, 3phase installation and fencing of the site | Lari | Lari/Kirenga | 2020-07-01 | 2021-06-01 | 2021-06-01 | 4000000 | Completed
FY 2021/2022
104 | Equipping of Wangige level 4 BH project | Kabete | Kabete | 2021-07-01 | 2022-06-01 | 2022-06-01 | 4000000 | Completed
105 | Operationalization of Kabunge and Gitithia BH | Lari subcounty | Lari/Kirenga | 2021-07-01 | 2022-06-01 | 2022-06-01 | 3500000 | Completed
106 | Procure, supply and lay of assorted pipes to extend water services for Kamangu distribution network | Kikuyu | Nachu | 2021-07-01 | 2022-06-01 | 2022-06-01 | 3900000 | Completed
107 | Procure, supply and lay of assorted pipes to extend water services for Uthiru distribution network | Kabete | Uthiru | 2021-07-01 | 2022-06-01 | 2022-06-01 | 4000000 | Completed
108 | Procure,supply and lay of assorted pipes to extend water services for Muthaara distribution network | Juja | Weiteithie/Juja | 2021-07-01 | 2022-06-01 | 2022-06-01 | 3500000 | Completed
FY 2022/2023
109 | Kahuho borehole water project - Drilling and equipping of new borehole at Kahuho town center to provide water to the unserved areas of kahuho | Kabete | Muguga | 2022-07-01 | 2023-06-01 | 2023-06-01 | 3338375 | Completed
FY 2023/2024
110 | Ndenderu water supply project - Procure and supply 5km of assorted pipes to extend water services in Kagongo | Kiambaa | Ndenderu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2411787 | Completed
111 | Ngegu Turitu water project - Supply and Delivery of Assorted Pipelines and Fittings to extend water services in Ngegu and Turitu | Kiambu | Ndumberi | 2023-07-01 | 2024-06-01 | 2024-06-01 | 4368186 | Completed
112 | Gatina Borehole Water Project - Supply and delivery of assorted pipelines and fittings for Gatina (Q=24m3/h) Borehole | Githunguri | Githiga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2204239 | Completed
113 | Ngochi Borehole Water Project - Supply and delivery of assorted pipelines and fittings for Ngochi (Q=29m3/h) Borehole | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2102363 | Completed
114 | Mitahato Borehole Water Project - Supply and delivery of assorted pipelines and fittings for Mitahato (Q=9m3/h) Borehole | Githunguri | Ngewa | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1858829 | Completed
115 | Gathangari Borehole Water Project - Supply and delivery of assorted pipelines and fittings for Gathangari (Q=28m3/h) Borehole | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2882750 | Completed
116 | Jamaica/Mukua Borehole Water Project - Supply and delivery of assorted pipelines and fittings for Jamaica/Mukua Borehole | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2994737 | Completed
117 | Supply & Delivery of Pipes & Fittings for Ikinu Primary School Borehole Water Project | Githunguri | Ikinu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2698379 | Completed
118 | Ondiri Police Post – Ziwani Water Supply Project - Procure, supply and delivery of 3.5km of assorted pipelines and fittings to serve/extend services in Ziwani and Rumwe areas | Kikuyu | Kikuyu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2812000 | Completed
119 | Gitaru-Kingeero-Wangige Water Supply Project - Procure, supply and delivery of 4.2km of assorted pipelines and fittings to serve/extend services in Kabete shopping centre | Kabete | Gitaru / Kabete | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3489000 | Completed
120 | Wangunyu Borehole Water Project | Kiambaa | Ndenderu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 488000 | Completed
121 | Gathanje Village Water Project - Drilling and equipping of Gathanje Village Borehole with pump | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 5184490 | Completed
122 | Gathanje Village Water Project-Installation of solar power, | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1955392 | Completed
123 | Gathanje Village Water Project-Construction of 18m high elevated tower and installation of 2 No. 10m3plastic tank | Githunguri | Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2522700 | Completed
124 | Kenyatta Road Water Project - Procure, supply, deliver and lay 10km assorted pipelines and fittings to extend services to Upcoming estates along Kenyatta road | Juja & Gatundu South | Theta & Ngenda | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2671200 | Completed
125 | Kiganjo & Komothai Water Distribution Project - Supply of 6.5km assorted pipes and fittings for Githiurure, Gatina, Gathiru, Gateiguru, Gatei, Gathaite and Marigi villages | Gatundu South,Githunguri | Kiganjo & Komothai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2231250 | Completed
126 | Supply of Plastic Tanks - Procure and supply 26 No. 10m3 plastic tank to institution and special groups | Various subcounties | Various wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2860000 | Completed
127 | Karura Gachie Water Distribution Project - Procure, supply and delivery of 8km assorted pipelines and fittings to serve/extend services to Karura and Gachie areas | Kiambaa | Ndenderu / Kihara | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3640476 | Completed
128 | Tiekunu water project – Supply and deliver 9km assorted pipelines and fittings to serve/extend services in Ndeiya and Kijabe | Limuru | Ndeiya | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2992098 | Completed
129 | Kijabe Last Mile water project -Procure, supply, deliver and lay of 12km assorted pipelines and fittings to serve/extend services in Kijabe | Lari | Kijabe | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2482998 | Completed
130 | Loromo Water Distribution Project - Supply and delivery of assorted pipes and fittings for Loromo Area Residents | Limuru | Bibirioni | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2998297 | Completed
131 | Supply, deliver and lay 2.6km OD 110 rising main from Riu borehole to Gichuri Memorial Primary School in Gikambura | Kikuyu | Karai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3880548 | Completed
132 | Supply and delivery of 1.7 km assorted pipelines and fittings for Muthurwa Water distribution | Kiambaa | Karuri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1935151 | Completed
133 | Lari DCC Borehole Project | Lari | Kijabe | 2023-07-01 | 2024-06-01 | 2024-06-01 | 12000000 | Completed
134 | Supply of pipes and fittings to serve Njunu | Kiambu | Ndumberi | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1333269 | Completed
135 | Ondiri Maii hii Borehole Water Project | Kikuyu | Karai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 15744554 | Completed
136 | Ngoliba Ward - Distribution Network Pipes | Thika | Ngoliba | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2445800 | Completed
137 | Gatuanyaga water project- Supply and delivery of pipes and fittings for gatuanyaga ward distribution network pipes | Thika | Gatuanyaga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3253733 | Completed
138 | Nguirubi and Kiawanda Water Distribution Project - Supply of assorted pipelines and fittings to extend water services to Nguirubi and Kiawanda Primary | Limuru | Ndeiya | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2997282 | Completed
139 | Rehabilitation of 4 Existing Boreholes within Githunguri – Gatina, thuita,gathaithi,mitahato | Githunguri | Ngewa, Githiga, Komothai, Githunguri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2156650 | Completed
140 | Water supply in Ndiuni, Kiawanda, Kiamwikamba, Connerstone, Mithuri, Tutu, Thigio Police, Gichungo Nduma, Gitutha and Lower Gichungo | Limuru | Ndeiya | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2308303 | Completed
141 | Limuru Central Water Distribution Project - Supply of assorted pipes and fittings for Limuru Central | Limuru | Limuru Central | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2612734 | Completed
142 | Construction of Limuru Town and Bibirioni Cemetery toilet | Limuru | Bibirioni | 2023-07-01 | 2024-06-01 | 2024-06-01 | 999000 | Completed
143 | Drilling of 250m Deep Borehole at Komothai Coffee Growers | Githunguri | Komothai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2414200 | Completed
144 | Marengeta Community Water Project - Installation of booster pump and solar, Supply and delivery of Pipes and Installation of 2 No. 10m3 plastic tanks on an 18m high steel tower | Kikuyu | Nachu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 4594974 | Completed
145 | Drilling of Gatuanabu borehole | Kabete | Muguga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2598640 | Completed
146 | Drilling of Mariaini borehole | Gatundu North | Gituamba | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3696000 | Completed
147 | Drilling of Komo borehole | Thika | Gatuanyaga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2307756 | Completed
148 | Drilling of Nderu borehole | Limuru | Ndeiya | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2265296 | Completed
149 | Drilling of Njiku borehole | Kiambaa | Karuri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2431296 | Completed
150 | Drilling Equipping of a new borehole at Karuri Primary School | Kiambaa | Karuri | 2023-07-01 | 2024-06-01 | 2024-06-01 | 4767690 | Completed
151 | Gatono, Nguna , Magumu & Kianganga Water Supply Project - Procure, supply and delivery of 8.5 km assorted pipelines (DN90-DN32) and fittings to extend services to Gatono, Nguna, Magumu & Kianganga. | Gatundu North | Chania & Mang’u | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2699027 | Completed
152 | Procure and supply 30 No. 10m3 plastic tank to institution and special groups | County-wide | County-wide | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1410000 | Completed
153 | Rehabilitation of Uthiru toilet | Kabete | Uthiru | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2996070 | Completed
154 | Equipping of the Riu-Nderi (Q=55m3/h) | Kikuyu | Karai | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2295427 | Completed
155 | Supply and Delivery of Assorted Water Pipelines and Fittings for Limuru Water Supply Company Distribution Network. Mirangine | Lari | Kinale | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2984071 | Completed
156 | Ngegu Turitu Water Project - Supply and installation of 4No.10m3 plastic tanks on an 18m High Steel Elevated Tower at Turitu Market | Kiambu | Ndumberi | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3452400 | Completed
157 | Lari Kirenga Water Supply Project - Procure, supply, deliver and lay of 13.2km assorted pipelines and fittings to serve/extend services in Githuya, Kibuto, Chaka, Gibuto and Kanyekine | Lari | Lari Kirenga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3669840 | Completed
158 | Karamba-ini Gatono Distribution Project - Assorted 8.5km pipes from borehole in Karamba-ini in Limuru East to Gatono village | Limuru | Limuru East | 2023-07-01 | 2024-06-01 | 2024-06-01 | 6592278 | Completed
159 | Construction of Bomboini and Kanyayo cemetery toilet | Kikuyu | Nachu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 995720 | Completed
160 | Construction of Nyathuna and Gathiga Cemetery toilet | Kabete | Nyathuna | 2023-07-01 | 2024-06-01 | 2024-06-01 | 996618 | Completed
161 | Renguti water project Borehole Project | Kikuyu | Nachu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 20100000 | Completed
162 | Repair of Kangoki Office Block | Thika | Kamenu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2431400 | Completed
163 | Procurement of materials of 14 No. Skips | Across wards | Across wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2987026 | Completed
164 | Fabrication of 42 No. triple waste bins | Across wards | Across wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2949909 | Completed
165 | Procurement of materials for 28 skips | Across wards | Across wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 5601932 | Completed
166 | Procurement 2 No. Dump trucks | Kikuyu and Limuru | Kikuyu and Limuru | 2023-07-01 | 2024-06-01 | 2024-06-01 | 23000000 | Completed
167 | Procurement of 1 No. Compactor | Thika | Thika Township | 2023-07-01 | 2024-06-01 | 2024-06-01 | 20000000 | Completed
168 | Fabrication of 14 No. Skips | County Wide | County Wide | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1140000 | Completed
169 | Fabrication of 125 No. street litter bins | County Wide | County Wide | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2997875 | Completed
170 | Procurement of materials for 14 skips | Across Subcounties | Across wards | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2800966 | Completed
171 | Construction of Kiambaa Gititu and Muguga cemetery toilet | Kabete | Muguga | 2023-07-01 | 2024-06-01 | 2024-06-01 | 999000 | Completed
172 | Rehabilitation of 10 No. public toilets Lot 2 – Limuru (Limuru Food market, Limuru buspark), Kikuyu (Gikambura mkt, Thogoto psf),Kabete (muguga/kiambaa mkt),Kiambaa (Kihara, Ruaka), Riabai and Kiambu public and private toilets | Limuru, Kikuyu,Kabete, Kiambaa, Kiambu | Limuru central, Kikuyu,Karai, Muguga, Riabai, Kihara | 2023-07-01 | 2024-06-01 | 2024-06-01 | 4875017 | Completed
173 | Procurement of materials and fabrication of 125 litre bins | County Wide | County Wide | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2950000 | Completed
174 | Fabrication of 42 skips | County Wide | County Wide | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3567050 | Completed
175 | Supply and delivery of Hardcore for Kangoki | Thika | Kamenu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2032518 | Completed
176 | Construction of guard house and pit latrine in Kangoki | Thika | Kamenu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2913330 | Completed
177 | Construction of Makongeni buspark toilet | Thika | Kamenu | 2023-07-01 | 2024-06-01 | 2024-06-01 | 2579120 | Completed
178 | Construction of Kahawa Sukari toilet - Public park | Ruiru | Kahawa Sukari | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1570464 | Completed
179 | Construction of Kahawa Sukari toilet - Shopping centre | Ruiru | Kahawa Sukari | 2023-07-01 | 2024-06-01 | 2024-06-01 | 1998480 | Stalled
180 | Construction of Mundoro Playground toilet | Gatundu South | Kiganjo | 2023-07-01 | 2024-06-01 | 2024-06-01 | 3290938 | Completed
FY 2024/2025
181 | Construction of Rironi and Kamirithu Cemetery toilets | Limuru | Limuru central | 2024-07-01 | 2025-06-30 | 2025-06-30 | 2397976 | Completed
182 | Construction of Kibichoi market Public Sanitation Facility | Githunguri | Komothai | 2024-07-01 | 2025-06-30 | 2025-06-30 | 3026701 | Completed
183 | Construction of Mwimuto shopping center Public Sanitation Facility | Kabete | Kabete | 2024-07-01 | 2025-06-30 |  | 3296270 | Ongoing
184 | Construction of Muchatha and Gathanga Cemetery Toilet | Kiambaa | Muchatha | 2024-07-01 | 2025-06-30 | 2025-06-30 | 1408971 | Completed
185 | Construction of Ngecha cemetery and Rutara cemetery toilets | Kikuyu | Karai / Ngecha Tigoni | 2024-07-01 | 2025-06-30 | 2025-06-30 | 3995000 | Completed
186 | Gitogothi borehole project - Supply and deliver 2.6km of assorted pipes and fittings for rising main from Gitogothi borehole to tank | Limuru | Limuru Central | 2024-07-01 | 2025-06-30 | 2025-06-30 | 4024174 | Completed
187 | Drilling and equipping Ngecha (Ha Wagacucu) borehole (Ward Dev Fund) | Limuru | Ngecha Tigoni | 2024-07-01 | 2025-06-30 | 2025-06-30 | 3392413 | Completed
188 | Improvement and maintenance of Kangoki main and access road | Thika | Kamenu | 2024-07-01 | 2025-06-01 |  | 1000000 | Ongoing
189 | Purchase of 1 No. Compactor | County wide | County wide | 2024-07-01 | 2025-06-01 | 2025-06-01 | 24000000 | Completed
190 | Procurement and Fabrication of 42No. Skip bins | County wide | County wide | 2024-07-01 | 2025-06-01 | 2025-06-01 | 19109050 | Completed
191 | Procurement and distribution of 125 No. litre single bins | 60 wards | 60 wards | 2024-07-01 | 2025-06-01 | 2025-06-01 | 5690000 | Completed
192 | Construction of soil and water conservation structure and farm ponds in identified farms | Gatundu North, Gatundu South, Kikuyu, Thika, Limuru | Chania, Kiganjo. Karai, Ngoliba, Ndeiya | 2024-07-01 | 2025-06-01 |  | 40600000 | Ongoing
193 | Komo borehole project - Equipping and solarization of Komo borehole | Thika | Gatuanyaga | 2024-07-01 | 2025-06-01 |  | 5966667 | Ongoing
194 | Gatuanabu borehole project - Equipping and solarization of Gatuanabu borehole | Kabete | Muguga | 2024-07-01 | 2025-06-01 |  | 4956946 | Ongoing
195 | Cianda borehole project - Equipping and solarization of Cianda borehole | Kiambu | Ndumberi | 2024-07-01 | 2025-06-01 |  | 5966667 | Ongoing
196 | Githunguri Gicamu borehole project – Drilling Equipping and solarization of Githunguri Gicamu BH | Kabete | Nyathuna | 2024-07-01 | 2025-06-01 |  | 9033333 | Ongoing
197 | Juja farm borehole project – Drilling Equipping and solarization of Juja farm BH | Juja | Kalimoni | 2024-07-01 | 2025-06-01 |  | 9033333 | Ongoing
198 | Kabuku borehole project – Drilling Equipping and solarization of Kabuku BH | Limuru | Ngecha Tigoni | 2024-07-01 | 2025-06-01 |  | 9033333 | Ongoing
199 | Storm water management/ Flood Control | Thika, Kabete and Juja | Kamenu, Uthiru and Juja | 2024-07-01 | 2025-06-01 |  | 40562974 | Ongoing
200 | Agro forestry | Lari, Githunguri, Juja, Gatundu South, Kahawa Sukari, Gitothua and Mwihoko | Kijabe, Nyanduma, Githiga, Githunguri, Ngewa, Witeithie, Ndarugu, Kiamwangi, Kahawa Sukari, Gitothua and Mwihoko | 2024-07-01 | 2025-06-01 |  | 6000000 | Ongoing
201 | Conservation of degraded riparian areas |  |  | 2024-07-01 | 2025-06-01 |  | 14000000 | Ongoing
202 | Climate proofing Ruiru Modern market | Ruiru | Biashara | 2024-07-01 | 2025-06-01 |  | 20100000 | Ongoing
STALLED PROJECTS
203 | Construction of Kahawa Sukari toilet - Shopping centre | Ruiru | Kahawa Sukari | 2022-07-01 | 2024-06-01 |  | 1998480 | Stalled
204 | Equipping of Karuri borehole | Kiambaa | Karuri | 2022-07-01 | 2023-06-01 |  | 4700000 | Stalled
205 | Drilling and equipping of Kona Mbaya borehole commenced in 2019 by KCG. Borehole on road reserve. Recommend alternative public site. | Thika | Ngoliba | 2019 July | 2020-06-01 |  | 14000000 | Stalled
206 | Drilling and equipping of Mutati borehole commenced in 2016 by KCG | Gatundu South | Kiganjo | 2016-07-01 | 2017-06-01 |  | 5000000 | Stalled